## North Carolina Transmission Planning Collaborative Process

Overview

The purpose of the North Carolina Transmission Planning Collaborative (NCTPC) Process is fully described in the Participation Agreement. In general, however, the NCTPC Process was established to:

- provide the Participants an opportunity to fully participate in the electric transmission planning process,

- preserve the integrity of the current reliability and least-cost planning processes,

- expand the transmission planning process to include analysis of increasing transmission capability to provide greater access to resources inside and outside the control areas of Duke and Progress, and

- ultimately develop a single coordinated transmission plan that includes both reliability and enhanced access plans that appropriately balances costs, benefits and risks associated with the use of transmission and generation resources.

The overall NCTPC Process includes two sets of studies that will be concurrent and iterative in nature. These are:

- Reliability Planning Process

- Enhanced Transmission Access Planning Process

Figure 1 below illustrates the major steps associated with the North Carolina Transmission Planning Collaborative Process.

- The general scope of these studies is outlined in the attached Appendix. It is expected that there will be considerable feedback and iteration between the Reliability Transmission Planning effort and the Enhanced Transmission Access Planning effort as solution alternatives for one affect the other.

- The Oversight Steering Committee (OSC) of the Participants is charged with managing the overall Process. The Planning Working Group (PWG) supports the development of the Process and performs the studies. The Transmission Advisory Group (TAG) provides advice and recommendation on the development of this Process and the study results.

- Reliability Planning Process

- This is the transmission planning process that has traditionally been used by the incumbent transmission owners to provide adequate, safe and reliable transmission service at the lowest reasonable cost. This transmission planning process is being enhanced to include the active participation of the Participants and input from the TAG.

In general, the reliability planning study process will follow the steps of the study process scope outlined in the Appendix. For the specific reliability planning process the OSC will approve the scope of the reliability study, oversee the study analysis being performed by the PWG, evaluate the study results, and approve the final reliability plan. The starting point of this reliability planning process will be the most recent reliability planning studies and current transmission upgrades plans. The PWG will perform the reliability studies based upon the OSC approved scope and prepare a report with the recommend transmission reliability solutions.

The final results of the Reliability Plan will included the estimated costs and schedules to provide the required transmission upgrades and/or additions required to maintain the necessary level of reliability to serve the native load of all the Participants. The reliability results will be reviewed with the TAG.

### Enhanced Transmission Access Planning Process

The Enhanced Transmission Access Planning (ETAP) Process will evaluate the means to increase transmission capability to provide greater access to resources inside and outside the control areas of Duke and Progress.

In general, the ETAP Process will follow the steps of the study process scope outlined in the Appendix. For the specific ETAP Process the OSC will approve the scope of the study (including any changes in the assumptions and study criteria for the studies used in the reliability analysis), oversee the study analysis being performed by the PWG, evaluate the study results, and approve the final enhanced access plan.

The starting point of the ETAP Process will be the Participants and TAG members proposing scenarios and interfaces to be studied. The proposed scenarios and interfaces will be compiled and evaluated by the OSC to determine which ones will be included for analysis in the current planning cycle. The PWG will perform the enhanced access studies based upon the OSC approved scope and prepare a report with possible recommend transmission solutions for increasing access on the interfaces evaluated.

The final results of the ETAP Process will include the estimated costs and schedules to provide the corresponding increased transmission capabilities. The OSC will evaluate the results and the PWG recommendations to determine if any enhanced access projects will provide a better alternative to planned reliability projects previously identified.  If so, the initial reliability plan will be modified accordingly. The enhanced access results will be reviewed with the TAG.

### Collaborative Transmission Plan

As described above, once the Reliability Plan and the Enhanced Transmission Access Plan sets of studies are completed they will be merged into a single Collaborative Transmission Plan that appropriately balances the costs, benefits and risks associated with the use of transmission and generation resources. The final plan will be reviewed with the TAG.

Once finalized this Collaborative Transmission Plan information will be used by the Participants in their individual resource planning processes to identify the least cost resources to meet their needs in evaluating alternative resource options which are then factored into their respective Integrated Resource Plans. Other stakeholders can use this information to similarly plan their related activities.

PWG evaluates reliability problems and current transmission upgrade  plans

PWG develops and  the  OSC approves the  reliability study scope

PWG performs analysis, identifies reliability problems, develops solutions with estimates of costs and schedules

Participants and TAG recommend scenarios and the OSC selects interface studies for analysis

PWG performs analysis, identifies access problems, develops solutions with estimates of costs and schedules

Reliability Planning

Enhanced Transmission Access Planning

OSC selects reliability and enhanced access solutions; checks for improved reliability through access solutions

OSC creates final draft Collaborative Plan

Feedback and Iterative Studies

Participants and TAG evaluate the reliability study results

Participants’ resource planning process

Participants and TAG evaluate the enhanced access results

TAG feedback on final draft Collaborative Plan

OSC approves final Collaborative Plan

PWG develops and  the OSC approves the  access study scope

Figure 1
North Carolina Transmission Planning Collaborative Process Flowchart

- Appendix

- North Carolina Transmission Planning Collaborative Process

- Transmission Planning Study Process - General Scope

The general scope for the overall study process for both the Reliability Planning and the Enhanced Transmission Access Planning activities involves essentially the same steps.  Depending of the specific goal of the evaluation being performed, different steps in this scope such as the assumptions, study criteria, methodology, etc. would be adjusted to reflect the elements of the particular analysis required to achieve that goal.

The typical study process includes the following steps:

#### Assumptions

- Select the study assumptions for the analysis

- The study assumptions normally include the following:

    - Years to study

    - Load levels to be studied (e.g., peak, shoulder and light loads)

    - Load forecasts

    - Resource Supply projections

    - Interchange capabilities

    - Firm Reservations including TRM / CBM

    - Transmission Contingencies

    - Special protection schemes, special operating schemes

    - Financial (e.g., time value of money, financing costs, duration of analysis for present value analyses, etc.)

#### Study Criteria

- Establish the criteria by which the study results will be measured

- The criteria with which results will promote consistency in the planning criteria used across the systems of the Participants, while recognizing differences between individual systems.

- Typical study criteria involves the following elements:

    - Reliability criteria – NERC Categories A, B and C; SERC, individual company criteria

    - Loss of generators in addition to loss of transmission elements

    - Technical limits including: Thermal, Voltage – both magnitude and phase angle, Stability, and Short Circuit

#### Case Development

- Prepare the base case model

- Develop change case models as required to evaluate different resource supply scenarios

#### Methodology

- Determine the methodologies that will be used to carry out the study

- Determine the specific software programs that will be utilized to perform the analysis

#### Technical Analysis and Study Results

- Perform the study analysis (thermal, voltage, stability and short circuit) and produce the results

- Study thermal and voltage limits first. Thermal limits are typically the most difficult to resolve and the most limiting, with voltage issues usually being identified within the same power-flow analyses

- Study stability and short circuit analysis as needed

#### Assessment and Problem Identification

- Evaluate the results to identify problems / issues. The key questions are:

  - What causes the issues / limits?

  - If the limit were fixed, what would the next limit be and what would limit it?

#### Solution Development

- Identify potential solutions to the problems / issues

- Test the effectiveness of the potential issues through additional studies (thermal, voltage, stability, short circuit) and modify the solutions as necessary such that all study criteria are met

- Perform financial analysis and rough scheduling estimate for each of the proposed transmission solutions (e.g., cost, cash flow, present value, incremental impacts on transmission rates)

#### Selection of Preferred Transmission Plan

- Comparison of alternatives and select the preferred solution alternatives – balancing of cost / benefit / risk

- Selection of a preferred set of transmission improvements that provide a reliable and the most cost effective transmission solution to meet customers needs while prudently managing the associated risks

#### Report on the Study Results

- Prepare a report on the results and recommended solutions for the final plan