| Period | PWG Activities |
| --- | --- |
| Jan 07 | 1/17 PWG Meeting 2006 STUDY REPORT - Support the presentation of the 2006 Study Report results to the TAG 2006 STUDY - COMPLETION OF 1200 MW RESOURCE OPTION SCENARIO - Complete the technical analysis associated with this scenario - Determine alternative solutions, estimated costs, and schedule 2007 STUDY SCOPE - Update the study scope as required based on direction provide from the OSC 2007 COMPARISON OF PLANNING STUDY ASSUMPTIONS/ STUDY CRITERIA/ METHODOLOGY - Evaluate and recommend changes to the 2006 planning study assumptions, study criteria, and methodology - Provide OSC report with recommended changes |
| Feb 07 | 2/13 PWG Meeting 2006 STUDY - COMPLETION OF 1200 MW RESOURCE OPTION SCENARIO - Select preferred alternatives - Begin drafting 2006 supplemental study report 2007 COMPARISON OF PLANNING STUDY ASSUMPTIONS/ STUDY CRITERIA/ METHODOLOGY - Integrate new planning assumptions, study criteria, and methodology into the 2007 study process as directed by the OSC 2007 STUDY SCOPE - Receive input and direction from OSC related to TAG requests for enhanced access scenarios - Update the 2007 Study Scope, if necessary 2007 CASE DEVELOPMENT - Develop base case models with new VSTE for 2012 and 2017 - All LSEs provide a list of resource supply option scenarios to PWG |
| Mar 07 | 3/14 PWG Meeting 2006 STUDY - COMPLETION OF 1200 MW RESOURCE OPTION SCENARIO - Finalize the 2006 supplemental study report and forward to the OSC for approval 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Begin work on base case and LSEs’ resource scenarios - Perform screens for the base reliability study |
| Apr 07 | 4/14 PWG Meeting 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Perform screens for the resource option scenarios |
| May 07 | 5/9 PWG Meeting 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Perform screens for the enhanced access scenarios as directed by the OSC |
| Jun 07 | 6/13 PWG Meeting 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Complete the technical analysis and problem identification for the base reliability, resource options, and the enhanced access scenarios. 2007 SOLUTION DEVELOPMENT - Begin to determine alternative solutions, estimated costs, and schedule |
| Jul 07 | 7/11 PWG Meeting 2007 SOLUTION DEVELOPMENT - Finalize the information related to alternative solutions, estimated costs, and schedule 2007 SELECTION OF SOLUTIONS - Begin to analyze and select preferred alternatives for Collaborative Plan |
| Aug 07 | 8/15 PWG Meeting 2007 SELECTION OF SOLUTIONS - Continue to analyze and select preferred alternatives for Collaborative Plan |
| Sep 07 | 9/12 PWG Meeting 2007 SELECTION OF SOLUTIONS - Finalize the selection of preferred alternatives for Collaborative Plan 2007 REPORT DEVELOPMENT - Prepare outline of the 2007 Collaborative Plan |
| Oct 07 | 10/xx PWG Meeting 2007 REPORT DEVELOPMENT - Begin drafting the report on the 2007 Collaborative Plan |
| Nov 07 | 11/xx PWG Meeting 2007 REPORT DEVELOPMENT - Finalize initial draft report on the 2007 Collaborative Plan and forward to OSC |
| Dec 07 | 12/xx PWG Meeting 2007 REPORT DEVELOPMENT - Complete the 2007 Collaborative Plan Report based on OSC direction. |