Status Report for period January 2007

| - Client Name (Client): | - Duke, Progress, ElectriCities, and NCEMC |
| --- | --- |
| - Project Number | - CDUKE-10605 – Independent Third Party Consulting for NC LSEs |

This Status Report is divided into the following sections:

A.	Accomplishments – Description of the accomplishments and activities this period

B.	Work in Progress – The projected activities for next period

- Work Not Started – Includes known activities in scope of work not currently underway

- Issues/Risks – Identifies any known issues or risk elements

- Travel Expenses – Provides an estimate of the planned travel activities for the next period

- Project Budget – Summarizes budgeted billings versus actual

- ACCOMPLISHMENTS/ACTIVITIES AS OF PREVIOUS PERIOD:

- The main activities over the last month were:

- OSC

  - Participated in the January 24th OSC meeting which was held in Raleigh.

  - Finalized and published the 2006 Report on the NC Collaborative Transmission Plan. (Major Milestone)

  - Prepared a cover letter to transmit the 2006 Report to the TAG and other stakeholders.

  - Supported the preparation of OSC meeting materials for the January meeting.

  - Prepared a 2007 NCTPC Study Scope for review and discussion with the OSC.

  - Prepared a 2007 PWG Work Plan for review and discussion with the OSC.

  - Prepared a 2007 OSC and TAG Work Plan to complement the draft 2007 PWG Work Plan for review and discussion at the OSC meeting.

  - Reviewed and commented on the planning process issue regarding transmission service requests and the NCTPC process.

- PWG

  - Participated in the January 17th PWG meeting which was held in Charlotte.

  - Continued to coordinate and develop various sections of the NCTPC Collaborative Transmission Plan report.

  - Supported the preparation and posting of PWG meeting materials for the January meeting.

  - Prepared and finalized a 2007 NCTPC Study Scope for review and discussion with the PWG.

  - Prepared and finalized a 2007 PWG Work Plan for review and discussion with the PWG.

  - Continued to discuss the compare and contrast of planning criteria, assumptions and methodologies for developing a recommendation for the OSC.

  - Continued to move forward with completing the 1200 MW resource option scenario analysis as directed by the OSC.

- TAG

  - Participated in the TAG meeting which was held on January 25th in Raleigh.

  - Distributed the 2006 NCTPC Collaborative Transmission Plan report to the TAG and solicited their comments prior to the scheduled TAG meeting.

  - Finalized and posted the TAG meeting agenda.

  - Prepared the TAG meeting materials including the presentations.

  - Supported the preparation and posting of TAG meeting materials for the January meeting.

  - Followed up on any action items resulting from the TAG meeting and/or inquires from TAG members.

  - Followed up on the solicitation of Enhanced Access Options from the stakeholders.

  - Continued to maintain the e-mail distribution list.

- Gestalt

  - Posted OSC, PWG and TAG meeting materials on the NCTPC website.

B.   WORK IN PROGRESS/PLANNED FOR NEXT PERIOD:

The major activities planned and anticipated during the next month include:

- OSC

  - Next OSC meeting is scheduled for March 1st in Charlotte.

  - Support the preparation of OSC meeting materials for the March meeting.

  - Comment on proposed Enhanced Transmission Access scenarios and interfaces for study and provide input to OSC.

  - Prepare a TAG memo on the Enhanced Transmission Access analysis for review and discussion at the OSC meeting.

- PWG

  - Next PWG meeting is scheduled for February 15th in Raleigh.

  - Support the preparation and posting of PWG meeting materials for the next scheduled meeting.

  - Continue to move forward with completing the 1200 MW resource option scenario analysis as directed by the OSC. Begin drafting 2006 supplemental study report.

  - Continue with 2007 case development and decide on resource supply options for the 2007 study.

  - Comment on proposed Enhanced Transmission Access scenarios and interfaces for study and provide input to PWG.

- TAG

  - Follow up on any action items resulting from the January TAG meeting and/or inquires from TAG members.

  - Prepare and send the TAG a reminder memo on the Enhanced Transmission Access Option scenarios.

  - Collate Enhanced Transmission Access Option scenarios received from TAG or Participants.

  - Posting of TAG meeting information, as required.

- Activities NOT STARTED:

- .None

- ISSUES/RISKS:

List any major issues that could affect any of the deliverables, i.e. availability of staff, major technical issues, etc.

- No issues or problems to report

- TRAVEL EXPENSES

List of planned travel for the next month and estimate of travel expenses:

- Rich Wodyka

  - Attend PWG meeting in Raleigh on February 15th.  (Expenses $500.00)

  - Attend OSC meeting in Charlotte on March 1st.  (Expenses $1200.00)

- Pam Kozlowski

  - Attend PWG meeting in Raleigh on February 15th.  (Expenses $400.00)

- PROJECT BUDGET REPORT

Through the end of January 2007, the project is currently on target and slightly over budget due to initial startup phase consuming more time than budgeted and factoring in the initial website development costs which were not part of the original planned activities.

Total Project Budget Estimate = $ 492,708.00 without travel expenses or the website development budget of $18,720.

Actual Billing	$35,626 for January 2007

$500,603 is the Project Total to date (August 2005 thru January 2007) which includes both the actual travel expenses ($40,487) and the website development costs ($22,520).