Status Report for period February 2007

| - Client Name (Client): | - Duke, Progress, ElectriCities, and NCEMC |
| --- | --- |
| - Project Number | - CDUKE-10605 – Independent Third Party Consulting for NC LSEs |

This Status Report is divided into the following sections:

A.	Accomplishments – Description of the accomplishments and activities this period

B.	Work in Progress – The projected activities for next period

- Work Not Started – Includes known activities in scope of work not currently underway

- Issues/Risks – Identifies any known issues or risk elements

- Travel Expenses – Provides an estimate of the planned travel activities for the next period

- Project Budget – Summarizes budgeted billings versus actual

- ACCOMPLISHMENTS/ACTIVITIES AS OF PREVIOUS PERIOD:

- The main activities over the last month were:

- OSC

  - The February OSC meeting was postponed and rescheduled to March 1st in Charlotte.

  - Supported the preparation of OSC meeting materials for the March 1st meeting.

  - Updated the 2007 overall NCTPC Work Plan for review and discussion with the OSC.

  - Updated the Guidelines for including LSE Resources in the base planning models for discussion with the OSC.

  - Prepared for OSC discussion of FERC Order 890 related to Regional Transmission Planning.

- PWG

  - Participated in the February 15th PWG meeting which was held in Raleigh and the February 27th teleconference meeting.

  - Supported the preparation and posting of PWG meeting materials for the February meetings.

  - Continued to move forward with completing the 1200 MW resource option scenario analysis as directed by the OSC.

  - Prepared a report outline and the first draft of the Supplemental Report on the 1200 MW scenario to the 2006 NCTPC Collaborative Transmission Plan Report.

  - Updated the 2007 PWG Work Plan for review and discussion with the PWG.

  - Continued with 2007 case development and discussing resource supply options for the 2007 study.

  - Continued to discuss the compare and contrast of planning criteria, assumptions and methodologies for developing a recommendation for the OSC.

- TAG

  - Followed up on action items resulting from the January TAG meeting and/or inquires from TAG members.

  - Followed up on the solicitation of Enhanced Access Options from the stakeholders.

  - Continued to maintain the e-mail distribution list.

- Gestalt

  - Posted OSC, PWG and TAG meeting materials on the NCTPC website.

B.   WORK IN PROGRESS/PLANNED FOR NEXT PERIOD:

The major activities planned and anticipated during the next month include:

- OSC

  - The March OSC meetings are scheduled for March 1st in Charlotte and March 21st in Charlotte.

  - Support the preparation of OSC meeting materials for the March meetings.

  - Continue to develop the Guidelines for including LSE Resources in the base planning models for review by the OSC.

  - Develop a press release for achieving the first milestone of the NCTPC Process – publication of the first Collaborative Transmission Plan.

  - Continue to evaluate FERC Order 890 related to Regional Transmission Planning for discussion with OSC.

- PWG

  - Next PWG meeting is scheduled for March 14th in Aberdeen. Also a March 5th teleconference meeting is scheduled.

  - Support the preparation and posting of PWG meeting materials for the next scheduled meeting.

  - Continue to move forward with completing the 1200 MW resource option scenario analysis as directed by the OSC.

  - Finalize the 2006 Supplemental Study Report and forward to the OSC for their review and approval.

  - Continue with 2007 case development and decide on resource supply options for the 2007 study.

- TAG

  - Follow up on any action items resulting from the January TAG meeting and/or inquires from TAG members.

  - Set the date, time and location for the April TAG meeting.

  - Prepare and send the TAG a memo to hold the date for the April TAG meeting.

  - Prepare and send the TAG a memo on the meeting time and location along with the proposed meeting agenda.

  - Send the TAG the Supplemental Study Report to the 2006 Collaborative Transmission Plan Report for their review and discussion at the April TAG meeting.

  - Posting of TAG meeting information, as required.

- Activities NOT STARTED:

- .None

- ISSUES/RISKS:

List any major issues that could affect any of the deliverables, i.e. availability of staff, major technical issues, etc.

- No issues or problems to report

- TRAVEL EXPENSES

List of planned travel for the next month and estimate of travel expenses:

- Rich Wodyka

  - Attend OSC meeting in Charlotte on March 1st.  (Expenses $1200.00)

  - Attend PWG meeting in Aberdeen on March 14th.  (Expenses $500.00)

  - Attend OSC meeting in Charlotte on March 21st.  (Expenses $1200.00)

- Pam Kozlowski

  - Attend PWG meeting in Aberdeen on March 14th.  (Expenses $500.00)

- PROJECT BUDGET REPORT

Through the end of February 2007, the project is currently on target and slightly over budget due to initial startup phase consuming more time than budgeted and factoring in the initial website development costs which were not part of the original planned activities.

Total Project Budget Estimate = $ 492,708.00 without travel expenses or the website development budget of $18,720.

Actual Billing	$23,340 for February 2007

$523,943 is the Project Total to date (August 2005 thru February 2007) which includes both the actual travel expenses ($40,910) and the website development costs ($22,520).