| Period | PWG Activities | OSC Activities | TAG Activities |
| --- | --- | --- | --- |
| Jan 07 | 1/17 PWG Meeting 2006 STUDY REPORT - Develop TAG meeting presentation materials - Support the presentation of the 2006 Study Report results to the TAG 2006 STUDY - COMPLETION OF 1200 MW RESOURCE SUPPLY OPTION SCENARIO - Continue the technical analysis associated with this scenario - Determine alternative solutions, estimated costs, and schedule 2007 STUDY SCOPE - Update the study scope as required based on direction provide from the OSC 2007 COMPARISON OF PLANNING STUDY ASSUMPTIONS/ STUDY CRITERIA/ METHODOLOGY - Evaluate and recommend changes to the OSC on planning study assumptions, study criteria, and methodology - Provide the OSC a report with recommended changes to be incorporated into the 2007 study process and changes that will be analyzed during 2007 for possible inclusion in future analysis | 1/24 OSC Meeting 2006 STUDY REPORT - Review and discuss any comments or questions provided by the TAG related to the 2006 Study Report - Review and comment on the TAG meeting presentation materials - Based on the TAG meeting comments and questions, finalize 2006 Study Report 2007 STUDY SCOPE - Review and comment on the 2007 Study Scope - Complete “Guidelines for including Base Case Resources” and provide direction to the PWG for the 2007 Study Scope 2007 COMPARISON OF PLANNING STUDY ASSUMPTIONS/ STUDY CRITERIA/ METHODOLOGY - Evaluate recommendations from the PWG on new planning assumptions, study criteria, and methodology. Provide direction to the PWG on what changes to incorporate into the 2007 study process and what changes should be analyzed during 2007 for possible inclusion in future analysis | 1/25 TAG Meeting 2006 STUDY REPORT - Receive presentation on the 2006 Study Report and provide comments to the OSC - Provide feedback to the OSC on the 2006 NCTPC Process 2007 STUDY SCOPE - Receive presentation on the 2007 Study Scope and provide comments to the OSC - Review and comment on the 2007 TAG Activity Schedule |
| Feb 07 | 2/15 PWG Meeting 2006 STUDY - COMPLETION OF 1200 MW RESOURCE SUPPLY OPTION SCENARIO - Select preferred alternatives - Begin drafting 2006 supplemental study report 2007 COMPARISON OF PLANNING STUDY ASSUMPTIONS/ STUDY CRITERIA/ METHODOLOGY - Integrate new planning assumptions, study criteria, and methodology into the 2007 study process as directed by the OSC 2007 STUDY SCOPE - Receive input and direction from OSC related to TAG requests for enhanced transmission access scenarios - Update the 2007 Study Scope, if necessary 2007 CASE DEVELOPMENT - Begin developing base case models with new VSTE for 2012 and 2016 - All LSEs provide list of DNRs with dispatch order and a list of resource supply option scenarios to PWG |  | 2007 STUDY SCOPE - Provide input to the OSC on proposed Enhanced Transmission Access scenarios and interfaces for study |
| Mar 07 | 3/14 PWG Meeting 2006 STUDY - COMPLETION OF 1200 MW RESOURCE SUPPLY OPTION SCENARIO - Finalize the 2006 Supplemental Study report and forward to the OSC for approval 2007 COMPARISON OF PLANNING STUDY ASSUMPTIONS / STUDY CRITERIA / METHODOLOGY - Develop an action plan as directed by the OSC for those planning assumptions, study criteria, and methodology changes that will be analyzed in 2007 for inclusion in future studies 2007 CASE DEVELOPMENT - Complete developing base case models with new VSTE for 2012 and 2016 - Develop recommendation on resource supply option scenarios for inclusion in the 2007 studies 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Begin to develop the base case and LSEs’ resource supply option scenarios models TAG MEETING SUPPORT - Develop TAG meeting presentation materials | 3/1 OSC Meeting 2007 STUDY SCOPE - Evaluate the TAG requests for enhanced transmission access scenarios and provide direction to the PWG on the 2007 Study Scope, if necessary 3/21 OSC Meeting 2006 STUDY - COMPLETION OF 1200 MW RESOURCE SUPPLY OPTION SCENARIO - Review and approve the 2006 Supplemental Study report and forward to the TAG for their information 2007 CASE DEVELOPMENT - Review and approve PWG recommendation on resource supply option scenarios for inclusion in the 2007 studies 2007 STUDY SCOPE - Provide feedback to TAG on what proposed Enhanced Transmission Access scenarios and interfaces will be included in the 2007 study TAG MEETING SUPPORT - Finalize the TAG meeting logistics and agenda items | - Receive feedback from the OSC on what proposed Enhanced Transmission Access scenarios and interfaces will be included in the 2007 study - Receive the 2006 Supplemental Study report |
| Apr 07 | 4/14 PWG Meeting TAG MEETING SUPPORT - Finalize the TAG meeting presentation materials 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Perform screens for the 2012 reliability base cases - Perform screens for the 2016 reliability base cases | 4/26 OSC Meeting TAG MEETING SUPPORT - Finalize the TAG meeting presentation materials 2006 SUPPLEMENTAL REPORT - Based on the TAG meeting comments and questions, finalize 2006 Supplemental Study report 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Receive a progress report from the PWG | 4/26 TAG Meeting - Receive presentation on the 2006 Supplemental Study report and provide comments to OSC - Receive a progress report on the 2007 Planning study activities and results |
| May 07 | 5/9 PWG Meeting 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Perform screens for the 2016 resource supply option scenarios | 5/23 OSC Meeting 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Receive a progress report from the PWG |  |
| Jun 07 | 6/13 PWG Meeting 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Complete the technical analysis and problem identification for the 2012 and 2016 reliability base cases and 2016 resource supply options 2007 SOLUTION DEVELOPMENT - Begin to determine and evaluate alternative solutions, estimated costs, and schedule estimates 2006 COLLABORATIVE PLAN UPDATE - PWG will prepare a report on the implementation status of the transmission projects identified in the 2006 Collaborative Plan for review with the OSC | 6/20 OSC Meeting 2007 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION 2007 SOLUTION DEVELOPMENT - Receive a progress report from the PWG |  |
| Jul 07 | 7/11 PWG Meeting 2007 SOLUTION DEVELOPMENT - Finalize the information related to alternative solutions, estimated costs, and schedule 2007 SELECTION OF SOLUTIONS - Begin to analyze and select preferred alternatives for 2007 Collaborative Plan | 7/17 OSC Meeting 2007 SOLUTION DEVELOPMENT 2007 SELECTION OF SOLUTIONS - Receive a progress report from the PWG 2006 COLLABORATIVE PLAN UPDATE - OSC will review and comment on the PWG report on the implementation status of the transmission projects identified in the 2006 Collaborative Plan |  |
| Aug 07 | 8/15 PWG Meeting 2007 SELECTION OF SOLUTIONS - Continue to analyze and select preferred solution alternatives for 2007 Collaborative Plan TAG MEETING SUPPORT - Develop TAG meeting presentation materials | 8/14 OSC Meeting 2007 SELECTION OF SOLUTIONS - Receive a progress report from the PWG TAG MEETING SUPPORT - Review and comment on the TAG meeting presentation materials |  |
| Sep 07 | 9/12 PWG Meeting 2007 SELECTION OF SOLUTIONS - Finalize the selection of preferred solutions for inclusion in the 2007 Collaborative Plan 2007 REPORT DEVELOPMENT - Prepare report outline for the 2007 Collaborative Plan | 9/13 OSC Meeting 2007 SELECTION OF SOLUTIONS - Receive a progress report from the PWG 2007 REPORT DEVELOPMENT - Review and approve outline of the 2007 Collaborative Plan | TAG Meeting - Receive a progress report on the Reliability Planning studies |
| Oct 07 | 10/17 PWG Meeting 2007 REPORT DEVELOPMENT - Begin drafting the report on the 2007 Collaborative Plan 2007 COMPARISON OF PLANNING STUDY ASSUMPTIONS/ STUDY CRITERIA/ METHODOLOGY - Develop a report on recommendations for planning assumptions, study criteria, and methodology changes that should be incorporated into future analysis | 10/11 OSC Meeting 2007 REPORT DEVELOPMENT - Receive a progress report from the PWG |  |
| Nov 07 | 11/8 PWG Meeting 2007 REPORT DEVELOPMENT - Finalize initial draft report on the 2007 Collaborative Plan and forward to OSC | 11/15 OSC Meeting 2007 REPORT DEVELOPMENT - Review the initial draft report on the 2007 Collaborative Plan and provide comments to the PWG 2007 COMPARISON OF PLANNING STUDY ASSUMPTIONS/ STUDY CRITERIA/ METHODOLOGY - Review PWG report on recommendations for planning assumptions, study criteria, and methodology changes that should be incorporated into future analysis - Provide PWG direction on what changes should be incorporated into the 2008 planning analysis |  |
| Dec 07 | 12/6 PWG Meeting 2007 REPORT DEVELOPMENT - Complete the 2007 Collaborative Plan Report based on OSC direction - Develop TAG meeting presentation materials | 12/13 OSC Meeting 2007 REPORT DEVELOPMENT - Review and finalize the 2007 Collaborative Plan Report - Distribute the final draft 2007 Collaborative Plan Report to the TAG for their review and comment TAG MEETING SUPPORT - Review and comment on the TAG meeting presentation materials | - Receive and review a final draft of the 2007 Collaborative Transmission Plan report January 2008 TAG Meeting - Review and comment on the draft report of 2007 Collaborative Transmission Plan - Provide feedback to the OSC on the 2007 NCTPC Process - Review and comment on the 2008 TAG Activity Schedule |