2007 NCTPC Supplemental Study - Progress West Import

# Purpose of Study

Beginning in the 2010 timeframe, significant changes are postulated for the resources forecast to meet Progress West area load.   The study will assess resource supply option (RSO) scenarios for the Progress West area and determine the necessary upgrades to accommodate the RSOs. A supplemental report to the 2007 NCTPC Report will be developed that may include recommended changes to the NCTPC Collaborative Plan.

# Study Case Development (December 2007)

The previously developed 2012 and 2016 summer base cases will be adjusted to create the new 2012 and 2016 summer study cases.  The 2011-12 and 2015-16 winter cases must be fully developed from Duke’s internal winter cases.

| Study Cases |  | Interchange / Progress West TRM Interchange |  |  |
| --- | --- | --- | --- | --- |
|  |  | Duke | Progress East | Progress West |
| 2011-12 Winter | Base | 244 / 444 | -987 / -987 | -496 / -738 |
| 2011-12 Winter | 100 MW from Duke (2010 West Import) | 344 / 544 | -987 / -987 | -596 / -838 |
| 2011-12 Winter | 100 MW from Southern (2011 West Import) | 244 / 444 | -987 / -987 | -596 / -838 |
| 2012 Summer | Base | -471 / -271 | -978 / -978 | -496 / -738 |
| 2012 Summer | 100 MW from Duke (2010 West Import) | -371 / -171 | -978 / -978 | -596 / -838 |
| 2012 Summer | 100 MW from Southern (2011 West Import) | -471 / -271 | -978 / -978 | -596 / -838 |
| 2015-16 Winter | Base | -72 / 128 | -884 / -884 | -596 / -838 |
| 2016 Summer | Base | -877 / -677 | -876 / -876 | -596 / -838 |

Notes:	1. Positive interchange indicates a net export and negative interchange a net import.

2. In Progress West TRM cases, Progress West imports an additional 200 MW from Duke and 42 MW from AEP.

# Screen Study Cases (January 2008)

# Assess Screening Results and Develop Solutions (February 2008)

# Report on the Study Results (March 2008)

The PWG will compile all the study results and detail the necessary upgrades recommended to accommodate the RSOs studied including estimates of project costs and construction schedules. Following OSC review and direction the NCTPC Collaborative Plan may be modified. . The supplemental report would include a comprehensive summary of all the study activities including possible changes to the Collaborative Plan. The supplemental report should be complete by March 2008 to facilitate engineering activities needed to support the resource changes occurring in the 2010 timeframe.