| Period | PWG Activities | OSC Activities | TAG Activities |
| --- | --- | --- | --- |
| Jan 08 | 1/8 PWG Meeting 2007 STUDY REPORT - Incorporate TAG comments in 2007 Study Report for approval by the OSC 2007 SUPPLEMENTAL STUDY - Review results from Progress West Import analysis - Determine alternative solutions, estimated costs, and schedule - Begin drafting 2007 Supplemental Report 2008 STUDY SCOPE - Develop draft 2008 Study Scope - Request input from OSC regarding individual Participant’s RPS requirements and their Resource Planning guidance for developing wind resource supply option scenarios (MWs, sites, etc.) DOCUMENTATION ON COST ESTIMATES - Develop documentation on how cost estimates were developed for the 2007 Collaborative Transmission Plan | 1/16 OSC Meeting 2007 STUDY REPORT - Review and discuss any comments or questions provided by the TAG related to the 2007 Study Report - Finalize and approve 2007 Study Report - Distribute to the TAG and post on the NCTPC website the final 2007 Study Report 2008 STUDY SCOPE - Review and comment on the 2008 Study Scope - Finalize and approve 2008 Study Scope - Distribute to the TAG and post on the NCTPC website the final 2008 Study Scope - Request TAG provide input by 2/11 on proposed Enhanced Transmission Access scenarios and interfaces for study DOCUMENTATION ON COST ESTIMATES - Receive report from PWG | 2007 STUDY REPORT - Receive final 2007 Study Report 2008 STUDY SCOPE - Review and comment on the 2008 Study Scope - Receive request from OSC to provide input by 2/11 on proposed Enhanced Transmission Access scenarios and interfaces for study |
| Feb 08 | 2/6 PWG Meeting 2007 SUPPLEMENTAL STUDY - Completion of Progress West Import Analysis - Select preferred alternatives - Continue drafting 2007 Supplemental Report 2008 STUDY SCOPE - Receive information from PEC on potential new methodologies/processes for determination of AFC, ATC, and TRM. - Update the 2008 Study Scope, if necessary 2008 CASE DEVELOPMENT - Begin developing base case models with new VSTE for 2013 and 2018 - All LSEs provide list of DNRs with dispatch order and a list of resource supply option scenarios to PWG | 2/13 OSC Meeting 2008 STUDY SCOPE - Evaluate the TAG requests for enhanced transmission access scenarios and provide direction to the PWG on the 2008 Study Scope, if necessary - Provide input to PWG regarding individual Participant’s RPS requirements and their Resource Planning guidance for developing wind resource supply option scenarios | 2008 STUDY SCOPE - Provide input to the OSC by 2/11 on proposed Enhanced Transmission Access scenarios and interfaces for study |
| Mar 08 | 3/5 PWG Meeting 2007 SUPPLEMENTAL STUDY - Finalize draft of the 2007 Supplemental Report and forward to the OSC for approval 2008 STUDY SCOPE - Receive input and direction from OSC related to TAG requests for enhanced transmission access scenarios - Update the 2008 Study Scope, if necessary 2008 CASE DEVELOPMENT - Complete developing base case models with new VSTE for 2013 and 2018 - Develop recommendation on resource supply option scenarios for inclusion in the 2008 studies 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Begin to develop the base case and LSEs’ resource supply option scenarios models TAG MEETING SUPPORT - Develop TAG meeting presentation materials | 3/12 OSC Meeting 2007 SUPPLEMENTAL STUDY - Review 2007 Supplemental Report and forward to the TAG for their input 2008 CASE DEVELOPMENT - Review and approve PWG recommendation on resource supply option scenarios for inclusion in the 2008 studies 2008 STUDY SCOPE - Provide feedback to TAG on what proposed Enhanced Transmission Access scenarios and interfaces will be included in the 2008 study TAG MEETING SUPPORT - Finalize the TAG meeting logistics and agenda items | 2007 SUPPLEMENTAL REPORT - Receive and comment on the 2007 Supplemental Report TAG Meeting - Receive presentation on the 2007 Supplemental Report and provide comments to OSC - Receive a progress report on the 2008 Planning study activities and results - Receive feedback from the OSC on what proposed Enhanced Transmission Access scenarios and interfaces will be included in the 2008 study |
| Apr 08 | 4/9 PWG Meeting 2007 SUPPLEMENTAL REPORT - Incorporate TAG comments in 2007 Supplemental Report for approval by the OSC 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Perform screens for the 2013 reliability base cases - Perform screens for the 2018 reliability base cases | 4/15 OSC Meeting 2007 SUPPLEMENTAL REPORT - Review and discuss any comments or questions provided by the TAG related to the 2007 Supplemental Report - Finalize and approve 2007 Supplemental Report - Distribute to the TAG and post on the NCTPC website the final 2007 Supplemental Report 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Receive a progress report from the PWG | 2007 SUPPLEMENTAL REPORT - Receive final 2007 Supplemental Report |
| May 08 | 5/7 PWG Meeting 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Perform screens for the 2018 resource supply option scenarios | 5/14 OSC Meeting 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Receive a progress report from the PWG |  |
| Jun 08 | 6/4 PWG Meeting 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Complete the technical analysis and problem identification for the 2013 and 2018 reliability base cases and 2018 resource supply options - Determine sensitivity analysis to be performed regarding “select” new TPL standards. Begin the technical analysis and problem identification on 2018 reliability base cases 2008 SOLUTION DEVELOPMENT - Begin to determine and evaluate alternative solutions, estimated costs, and schedule estimates 2007 COLLABORATIVE PLAN UPDATE - PWG will prepare a report on the implementation status of the transmission projects identified in the 2007 Collaborative Plan for review with the OSC | 6/11 OSC Meeting 2008 TECHNICAL ANALYSIS, PROBLEM IDENTIFICATION and SOLUTION DEVELOPMENT - Receive a progress report from the PWG 2007 COLLABORATIVE PLAN UPDATE - OSC will review and comment on the PWG report on the implementation status of the transmission projects identified in the 2007 Collaborative Plan - OSC will provide the report to the TAG |  |
| Jul 08 | 7/9 PWG Meeting 2008 SOLUTION DEVELOPMENT - Finalize the information related to alternative solutions, estimated costs, and schedule for problems identified with the 2013 and 2018 reliability base cases and 2018 resource supply options 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Continue sensitivity analysis regarding new TPL standards on 2018 reliability base cases 2008 SELECTION OF SOLUTIONS - Begin to analyze and select preferred alternatives for 2008 Collaborative Plan 2008 STUDY SCOPE - Receive and review results of PEC’s internal study to evaluate its current transformer rating assumptions; update 2008 Study Scope, if necessary | 7/xx OSC Meeting 2008 SOLUTION DEVELOPMENT 2008 SELECTION OF SOLUTIONS - Receive a progress report from the PWG |  |
| Aug 08 | 8/6 PWG Meeting 2008 SELECTION OF SOLUTIONS - Continue to analyze and select preferred solution alternatives for 2008 Collaborative Plan 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Begin to determine impacts of new TPL standards[, evaluate alternative solutions, estimated costs, and schedule estimates] TAG MEETING SUPPORT - Develop TAG meeting presentation materials | 8/xx OSC Meeting 2008 SELECTION OF SOLUTIONS - Receive a progress report from the PWG TAG MEETING SUPPORT - Review and comment on the TAG meeting presentation materials | TAG Meeting - Receive a progress report on the Reliability Planning and Enhanced Transmission Access Planning studies |
| Sep 08 | 9/11 PWG Meeting 2008 SELECTION OF SOLUTIONS - Finalize the selection of preferred solutions for inclusion in the 2007 Collaborative Plan 2008 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Complete sensitivity analysis and determination impacts of new TPL standards 2008 REPORT DEVELOPMENT - Prepare report outline for the 2008 Collaborative Plan | 9/xx OSC Meeting 2008 SELECTION OF SOLUTIONS - Receive a progress report from the PWG 2008 REPORT DEVELOPMENT - Review and approve outline of the 2008 Collaborative Plan |  |
| Oct 08 | 10/8 PWG Meeting 2008 REPORT DEVELOPMENT - Begin drafting the report on the 2008 Collaborative Plan | 10/xx OSC Meeting 2008 REPORT DEVELOPMENT - Receive a progress report from the PWG |  |
| Nov 08 | 11/5 PWG Meeting 2008 REPORT DEVELOPMENT - Finalize initial draft report on the 2008 Collaborative Plan and forward to OSC | 11/xx OSC Meeting 2008 REPORT DEVELOPMENT - Review the initial draft report on the 2008 Collaborative Plan and provide comments to the PWG |  |
| Dec 08 | 12/11 PWG Meeting 2008 REPORT DEVELOPMENT - Complete the 2008 Collaborative Plan Report based on OSC direction - Develop TAG meeting presentation materials | 12/xx OSC Meeting 2008 REPORT DEVELOPMENT - Review and finalize the 2008 Collaborative Plan Report - Distribute the final draft 2008 Collaborative Plan Report to the TAG for their review and comment TAG MEETING SUPPORT - Review and comment on the TAG meeting presentation materials | 2008 STUDY REPORT - Receive and comment on final draft of the 2008 Collaborative Transmission Plan report TAG Meeting - Receive presentation on the draft report of 2008 Collaborative Transmission Plan - Provide feedback to the OSC on the 2008 NCTPC Process - Review and comment on the 2009 TAG Activity Schedule |