| Period | Reliability Plan Action | Enhanced Access Plan Action |
| --- | --- | --- |
| Sept05 - Nov05 | Finalize scope, assumptions, and evaluation criteria for the reliability plan & obtain OSC approval |  |
| Dec05 - Jan06 | Build & finalize models w/ new VSTE |  |
| Feb06 – Mar06 | - Perform screens for the reliability plan - Report results to OSC |  |
| Apr06 |  | Develop scope, assumptions, and evaluation criteria for the enhanced access studies & obtain OSC approval |
| Apr06-May06 | - Determine alternatives, estimated costs and schedule, and select preferred alternatives for reliability plan - Report results to OSC & obtain OSC approval for preferred alternatives | OSC provides approved list of enhanced access requests |
| Jun06 | Final reliability plan & report to OSC. | Provide feedback to OSC on enhanced access requests (i.e., cost and schedule to perform studies) |
| Jul06-Aug06 |  | - Study enhanced access requests - Report results to OSC |
| Sept06-Oct06 |  | - Determine estimated schedule & costs of options to accommodate enhanced access requests, select preferred options - Report results to OSC - Obtain feedback from OSC |
| Sept06-Nov06 | Refine estimate of schedule & cost for collaborative plan. |  |
| Dec06 | Finalize collaborative plan & report to OSC. |  |