| Period | PWG Reliability Plan Action | PWG Enhanced Access Plan Action | OSC Activities |
| --- | --- | --- | --- |
| Sept05 - Nov05 | Recommend assumptions, criteria and reliability study scope for the combined Duke/Progress reliability plan and submit to OSC for approval prior to 11/2 OSC meeting |  | 11/2: OSC meeting to discuss compare/contrast document and reliability study scope submitted by PWG for reliability and plan |
| Dec05 - Jan06 | Build & finalize models w/ new VSTE | Discuss assumptions, criteria and enhanced access study methodology for the combined Duke/Progress enhanced access plan and submit a compare/contrast document and methodology to OSC for approval prior to 12/9 OSC meeting | 12/9: OSC meeting to approve reliability assumptions and criteria; OSC discusses enhanced access methodology assumptions, criteria and methodology 1/5: OSC meeting to approve enhanced assumptions, criteria and methodology [OSC reach out to TAG or have meeting with TAG to solicit enhanced access requests.] 1/15: Lists of requested enhanced access studies due from Participants and TAG (Carney & Locke to compile for 1/30 OSC mtg) 1/30: OSC meeting to discuss enhanced access study requests and draft preliminary study list |
| Feb06 – Mar06 | Perform screens for the reliability plan Report results to OSC prior to 3/30 | PWG receives preliminary list from OSC of enhanced access study requests on 2/28 Develop estimated costs and schedules for preliminary enhanced access request studies and provide to OSC prior to 3/30 | 2/28: OSC meeting to approve list of enhanced access requests for preliminary study; OSC submits list to PWG to estimate study costs and schedules 3/30: OSC meeting to review cost/schedule of preliminary enhanced access studies submitted by PWG |
| Apr06-May06 | Determine alternatives, estimated costs and schedule, and select preferred alternatives for reliability plan Report results to OSC prior to 5/1 & obtain OSC approval for preferred alternatives | PWG receives approved list from the OSC on 5/1 of enhanced access requests to be studied in detail | [OSC meeting to review the results of the reliability screens in the April time frame?] 5/1: OSC meeting to select enhanced access requests to be studied in detail and submit to PWG; OSC begins discussions of 2006/2007 budget for the NCTPC Process and Gestalt 5/2: OSC informs TAG of study status |
| Jun06 | Final reliability plan & report to OSC Prior to 6/30 | VSTE models available on 6/15 PWG provides potential alternatives to achieve desired levels of transfer capability and updates OSC on 6/30 PWG begins enhanced access studies (VSTE model version TBD, based on nature of requests and timing) | 6/30: OSC approves 2006/2007 NCTPC budget; PWG updates OSC on potential alternatives to achieve desired levels of transfer capability [After the OSC finalizes the reliability plan and accepts the report, meet with the TAG (also provide status of enhanced access studies).] |
| Jul06-Aug06 |  | PWG prepares a comparison of alternatives and identifies preferred alternatives to achieve requested transfer capabilities Provide OSC with planning-level estimates of construction costs and schedules for preferred alternatives for enhanced access projects prior to 7/30 | 7/30: OSC discusses potential enhanced access projects 8/31: OSC selects enhanced access projects and provides to PWG for refinement; OSC starts project cost allocation discussion [After the OSC selects the enhanced access projects for refinement, meet with the OSC [TAG??] to report on the selection.] |
| Sept06-Nov06 | Refine costs and schedules of reliability plan and report results to OSC prior to 10/20 Integrate/iterate reliability plan with enhancement plan and report results to OSC prior to 11/20 | PWG receives selected enhanced access projects on 8/31 Refine costs and schedules of enhanced access project plan and report results to OSC prior to 10/20 Integrate/iterate enhanced access plan with reliability plan and report results to OSC prior to 11/20 | 10/20: OSC reviews any refinements of enhanced access and reliability projects; OSC approves enhanced access projects/plan and submits to PWG for integration with reliability plan 11/20: OSC approves final reliability and enhanced access projects and combined reliability/enhanced access plan 11/21: OSC informs TAG of final collaborative plan |
| Dec06 |  |  | 12/15: OSC completes cost allocation and budget discussions for combined reliability and enhanced access plans |