| Period | PWG Activities - Reliability Plan | PWG Activities - Enhanced Transmission Access Plan | OSC Activities | TAG Activities |
| --- | --- | --- | --- | --- |
| Sept05 - Nov05 | PWG recommends assumptions and criteria for the combined Duke/Progress reliability plan and submits to OSC for approval prior to 11/2 OSC meeting |  | 11/2: OSC meeting to discuss compare/contrast document submitted by PWG for reliability and enhanced access plans |  |
| Dec05 - Jan06 | PWG finalizes base case models with new VSTE PWG finalizes Reliability Study Scope document and summary of Reliability Plan Compare and Contrast document prior to 1/5 OSC meeting LSEs provide preliminary list of scenarios to PWG by 1/16 PWG makes recommendation to OSC on scenarios to study prior to 1/30 OSC meeting | PWG discusses assumptions and criteria for the combined Duke/Progress enhanced access plan and submits a summary of the compare/contrast document to 1/30 OSC meeting | 12/9: OSC continues discussion of enhanced access assumptions and criteria 1/5: OSC meeting to approve Reliability Study Scope document and resolve any issues in the summary of the Reliability Plan Compare and Contrast document 1/30: OSC meeting to finalize enhanced access assumptions and criteria |  |
| Feb06 – Mar06 | PWG begins work on base case and LSEs’ resource scenarios PWG performs screens for the reliability plan PWG reports status to OSC prior to 3/30 | PWG finalizes the Enhanced Transmission Access Study Scope document and submits to the OSC for approval 3/7 PWG receives preliminary list of enhanced access study requests on 3/7 | 2/17: Lists of requested enhanced access studies due from Participants and TAG (Carney & Locke to compile for 2/17) 3/7: OSC meeting to discuss/approve the Enhanced Transmission Access Study Scope document and the list of enhanced access projects/alternatives for preliminary study; OSC submits list to PWG to estimate study costs and schedules 3/30: OSC reviews PWG activities and progress | 2/3: Meeting with TAG. Discuss: - Update on NCTPC Process - Comments on scope of TAG - Review 2006 activity schedule - Review reliability study scope - Request study scenarios for Enhanced Access Process 2/17: TAG members submit lists of requested studies for Enhanced Access Process |
| Apr06-May06 | PWG determines alternatives, estimated costs, and schedule, and selects preferred alternatives for reliability plan | PWG develops estimated costs and schedules to perform preliminary enhanced access studies and provides to OSC prior to 5/1 PWG on 5/1 receives approved list of enhanced access requests to be studied in detail (can be delayed) | 5/1: OSC Meeting - Review cost/schedule of preliminary enhanced access studies submitted by PWG - Select enhanced access requests and alternatives to be studied in detail and submitted to PWG - Begin discussions of 2007/2008 budget for the Process and Gestalt 5/2: OSC informs TAG of study status | May TAG meeting: - Update on reliability studies - Feedback on approved list of enhanced access studies - Review enhanced access study scope |
| Jun06 | PWG reports reliability plan results to OSC prior to 6/30 & obtains OSC approval for preferred alternatives |  | 6/30: OSC Meeting - Approve 2006/2007 NCTPC budget; - PWG reports reliability plan results and obtains approval for preferred alternatives |  |
| Jul06-Aug06 | PWG provides final reliability plan & report to OSC prior to 7/30 | PWG begins enhanced access studies PWG finalizes potential alternatives to achieve desired levels of transfer capability based on selected enhanced access requests by 8/30 PWG on 8/31 - updates OSC on the potential alternatives identified and the respective planning-level estimates of construction costs and schedules for the enhanced access projects - receives OSC’s selection of enhanced access projects | 7/31: OSC approves final reliability plan 8/31: OSC receives PWG update on enhanced access studies | August TAG Meeting - Review draft of Reliability Plan - Update on enhanced access studies |
| Sept06-Nov06 | PWG refines costs and schedules of reliability plan and reports results to OSC prior to 10/20 PWG integrates/iterates reliability plan with enhanced access plan and reports results to OSC prior to 11/20 | PWG refines costs and schedules of enhanced access projects/plan and reports results to OSC prior to 10/20 PWG integrates/iterates enhanced access plan with reliability plan and reports results to OSC prior to 11/20 | 9/7: OSC starts project cost allocation discussion; selects enhanced access projects and provides selection back to PWG for refinement 10/20: OSC reviews any refinements of enhanced access and reliability projects; OSC approves enhanced access projects/plan and submits to PWG for integration with reliability plan 11/20: OSC approves final reliability and enhanced access projects and combined reliability/enhanced access plan 11/21: OSC informs TAG of final collaborative plan | November TAG Meeting - Review final Collaborative Plan |
| Dec06 |  |  | 12/15: OSC completes cost allocation and budget discussions for combined reliability and enhanced access plans | 12/31: Provide feedback to OSC on process |