| Period | PWG Activities - Reliability Planning Studies | PWG Activities - Enhanced Transmission Access Planning Studies | OSC Activities | TAG Activities |
| --- | --- | --- | --- | --- |
| Sept05 - Nov05 | PWG recommends assumptions and criteria for the combined Duke/Progress reliability planning studies and submits to OSC for approval prior to 11/2 OSC meeting |  | 11/2: OSC meeting to discuss compare/contrast document submitted by PWG for reliability and enhanced access planning studies |  |
| Dec05 - Jan06 | PWG finalizes base case models with new VSTE PWG finalizes Reliability Study Scope document and summary of Reliability Study Compare and Contrast document prior to 1/5 OSC meeting LSEs provide preliminary list of resource supply options to PWG by 1/20 PWG Conference Call to finalize resource supply options on 1/24 (9-11am). PWG makes recommendation to OSC on resource supply options to study by 1/27 . | PWG discusses assumptions and criteria for the combined Duke/Progress enhanced access planning studies and submits a summary of the compare/contrast document to 1/30 OSC meeting | 12/9: OSC continues discussion of enhanced access assumptions and criteria 1/5: OSC meeting to approve Reliability Study Scope document and resolve any issues in the summary of the Reliability Study Compare and Contrast document 1/30: OSC meeting to finalize enhanced access assumptions and criteria 1/30: OSC to approve resource supply options to study |  |
| Feb06 – Mar06 | PWG begins work on base case and LSEs’ resource scenarios PWG performs screens for the reliability planning studies PWG reports status to OSC prior to 3/30 | PWG to review enhanced access options at PWG meeting on 2/21. PWG finalizes the Enhanced Transmission Access Study Scope document and submits to the OSC for approval 3/7 PWG receives approved list of enhanced access options for preliminary study on 3/7 | 2/17: Lists of enhanced access options requested for study due from Participants and TAG (Carney & Locke to compile for 2/17) 3/7: OSC meeting to discuss/approve the Enhanced Transmission Access Study Scope document and the list of enhanced access options for preliminary study; OSC submits list to PWG to estimate study costs and schedules 3/30: OSC reviews PWG activities and progress | 2/3: Meeting with TAG. Discuss: - Receive update on NCTPC Process - Review and comment on Scope of TAG - Review and comment on the 2006 TAG activity schedule - Provide input to OSC on study scenarios for Enhanced Access Process 2/17: TAG members submit lists of requested studies for Enhanced Access Process |
| Apr06-May06 | PWG determines alternatives, estimated costs, and schedule, and selects preferred solutions for problems identified in the reliability planning studies | PWG develops estimated costs and schedules to perform preliminary enhanced access planning studies and provides to OSC prior to 5/1 PWG on 5/1 receives approved list of enhanced access options to be studied in detail (can be delayed) | 5/1: OSC Meeting - Review cost/schedule of preliminary enhanced access planning studies submitted by PWG - Select enhanced access options to be studied in detail and submitted to PWG - Begin discussions of 2007/2008 budget for the Process and Gestalt 5/2: OSC informs TAG of study status | 2nd Quarter TAG meeting: - Receive update on reliability planning studies - Receive feedback on approved list of enhanced access planning studies |
| Jun06 | PWG reports reliability planning study results to OSC prior to 6/30 & obtains OSC approval for preferred alternatives |  | 6/30: OSC Meeting - Approve 2006/2007 NCTPC budget; - PWG reports reliability planning study results and obtains approval for preferred alternatives |  |
| Jul06-Aug06 | PWG provides final reliability planning study report to OSC prior to 7/30 | PWG begins enhanced access planning studies PWG finalizes potential alternatives to achieve desired levels of transfer capability based on selected enhanced access requests by 8/30 PWG on 8/31 - updates OSC on the potential alternatives identified and the respective planning-level estimates of construction costs and schedules for the enhanced access projects - receives OSC’s selection of enhanced access projects | 7/31: OSC approves final reliability planning study report 8/31: OSC receives PWG update on enhanced access planning studies | 3rd Quarter TAG Meeting - Review and comment on Reliability planning study results - Receive update on enhanced access planning studies |
| Sept06-Nov06 | PWG refines costs and schedules of reliability planning study results and reports results to OSC prior to 10/20 PWG integrates/iterates reliability planning study results with enhanced access planning study results and reports results to OSC prior to 11/20 | PWG refines costs and schedules of enhanced access projects and reports results to OSC prior to 10/20 PWG integrates/iterates enhanced access planning study results with reliability planning study results and reports results to OSC prior to 11/20 | 9/7: OSC starts project cost allocation discussion; selects enhanced access projects and provides selection back to PWG for refinement 10/20: OSC reviews any refinements of enhanced access and reliability projects; OSC approves enhanced access projects and submits to PWG for integration with reliability projects identified as solutions for problems in the reliability planning studies 11/20: OSC approves final reliability and enhanced access projects and combined reliability/enhanced access collaborative plan 11/21: OSC informs TAG of final collaborative plan | 4th Quarter TAG Meeting - Review and comment on Enhanced Access Study results - Review and comment on final combined Collaborative Plan |
| Dec06 |  |  | 12/15: OSC completes cost allocation and budget discussions for collaborative plan | 12/31: Provide feedback to OSC on the 2006 NCTPC Process |