PWG Meeting Agenda

July 18, 2006

Duke’s Energy Center

Conf Room is ECII-0582

Charlotte, NC

10:00 AM – 3:00 PM (EPT)

10:00 – 10:10	Administrative Issues

- Report on meeting facilities & logistics

- Review & approve June 20, 2006 PWG minutes

10:10 – 10:20	OSC Meeting Report

- Receive report from the June 27, 2006 OSC meeting

10:20 – 12:00	Reliability Study

- Report on status of action items relative to the reliability study from June 20, 2006 PWG meeting

- Review concise summary of PEC screening results of 600 MW import cases, including follow-up action items from June 20, 2006 PWG meeting

- Review PEC screening results of 1200 MW import cases

- Discuss solutions for phase angle, delta P and ancillary thermal issues regarding Richmond-Newport 500 kV line

12:00 – 12:30	Lunch

12:30 – 1:30		TAG Meeting

- Review and revise, if necessary, NCTPC Process Activity Schedule dated 03/24/06

- Develop/discuss presentations

1:30 – 2:00		Draft Reliability Plan

- Discuss format and development of:

  - Reliability project listing

- Baseline draft Reliability Plan

2:00 – 2:45		Transmission Cost Allocation Presentation and Discussion

2:45 – 3:00		Other Items

3:00			Adjourn

ACTION ITEM LOG

Planning Working Group Meeting

June 20, 2006

|  | Action Item | Assigned To | Due Date |
| --- | --- | --- | --- |
| 1a 1b | Follow-up on questions regarding 600 MW import cases and results. A list of follow-up items developed during the June 20th PWG meeting is attached to the minutes. Prepare concise summary of screening results of the 600 MW import cases, including Duke contingencies and monitored elements, and distribute | PEC PEC | 07/11/06 07/11/06 |
| 2 | Complete screening of the 1200 MW import cases and distribute results | PEC | 07/11/06 |
| 3a 3b | Post “Newport-Richmond” presentation given at June 20th PWG meeting on web site, identify conditions tested in the examples presented Continue looking at impact of potential solutions from the PWG’s brainstorming session on May 11th and additional operating procedure suggestions made at June 20th meeting | PEC PEC | 06/27/06 07/11/06 |
| 4a 4b 4c | Revise template for reporting reliability problem identified, solutions considered, solution recommended and justification for recommendation Update templates for Duke identified projects Complete templates for PEC identified projects, including: Newport – Richmond 500 kV line Wake 500/230 kV transformers Phase Shifter – Anson 230 kV Falls 230/115 kV transformer Marion – Mullins 115 kV line Camden 115 kV | Pam Kozlowski Duke PEC | 06/27/06 07/11/06 07/11/06 |
| 5a 5b | Draft project listing Develop draft “baseline” reliability plan | Pam Kozlowski | 07/11/06 |