## Sheet1
Baseline Reliability Project List
Project ID | Major Project | Project Description | Status | Primary Equipment Owner | Projected In-Service Date for Baseline Reliability Plan | Estimated Cost | Project Lead Time (Years) | Earliest Projected In-Service Date (1) | For Resource Supply Option (2)
| Cape Fear - Siler City Transmission Project | Add Cape Fear - Siler City 230 kV | Under Construction | PEC | Summer 2006 |  | 5
| Cape Fear - Siler City Transmission Project | Add new Siler City Substation | Under Construction | PEC | Summer 2006 |  | 5
| Richmond/Newport 500 kV Reliability Project | Solution under development |  |  | 2007 |  |  | 2004 | Duke or SOCO to CPLE
| Greater Falls Upgrades | Add Durham - Falls 230 kV | Planned | PEC | 2008-06-01 | 9000000 | 3
| Greater Falls Upgrades | Upgrade existing transmission lines on existing rights of way | Planned | PEC | 2008-06-01 |  | 3
| Greater Falls Upgrades | Upgrade two substations | Planned | PEC | 2008-06-01 | 35000000 | 3
| Rockingham-Wadesboro Transmission Project | Add Rockingham - Wadesboro - Bowman School 230 kV | Planned | PEC | 2009-06-01 | 10000000 | 4.5
| Rockingham-Wadesboro Transmission Project | Upgrade Rockingham 230 kV substation | Planned | PEC | 2009-06-01 |  | 4.5
| Rockingham-Wadesboro Transmission Project | Upgrade Rockingham West 115 kV substation | Planned | PEC | 2009-06-01 |  | 4.5
| Rockingham-Wadesboro Transmission Project | Convert Wadesboro 115 kV substation to 230 kV | Planned | PEC | 2009-06-01 |  | 4.5
| Fayetteville Area Upgrades | Reconductor Fayetteville - Fayetteville Fort Bragg - Woodruff 230 kV |  | PEC | 2012 |  |  | 2009 | Santee Cooper to CPLE
| Fayetteville Area Upgrades | Replace Fayetteville 230/115 kV transformers #1 & #2 |  | PEC | 2012 |  |  | 2010 | SCEG to CPLE
| Fayetteville Area Upgrades | Reconductor Fayetteville - Fayetteville East 230 kV |  | PEC | 2014 |  |  | 2010 | Santee Cooper to CPLE
|  | Install 18 Mvar capacitor at Franklinton 115 kV substation |  | PEC | 2011-06-01 | 500000 | 2 | 2011-06-01 | (3)
|  | Replace Laurinburg 230/115 kV transformers #1 & #2 |  | PEC | 2012 |  |  | 2009 | Santee Cooper to CPLE
|  | Add 2nd Falls 230/115 kV transformer |  | PEC | 2013-06-01 | 5000000 | 5 | 2012-06-01 | Duke to CPLE
|  | Reconductor Wateree - Great Falls 100 kV |  | Duke | 2011 |  |  | 2011 | (3)
|  | Replace Antioch 500/230 kV transformers #1 & #2 |  | Duke | 2014 | 15,000,000 to 20,000,000 | 5 | 2011 | 600 MW or 1200 MW from AEP to Duke
|  | Replace Parkwood 500/230 kV transformers #5 & #6 |  | Duke | 2015 | 15,000,000 to 20,000,000 | 5 | 2011 | Duke to CPLE
|  | Reconductor London Creek 230 kV lines (Peach Valley - Riverview #1 & #2) |  | Duke | 2016 | 20,000,000 to 25,000,000 | 3 | 2015 | Duke to CPLE
(1) Advancement of project based on 600 MW Resource Supply Options simulated in the 2006 reliability study
(2) 600 MW Resource Supply Option simulated in 2006 reliability study that results in the Earliest Projected In-Service Date
(3) Need for project not impacted by Resource Supply Options simulated in the 2006 reliability study