## Base Plan
DRAFT
Project ID | Major Project | Project Description | Status | Trans Owner | Projected In-Service Date for Baseline Reliability Plan | Estimated Cost ($M) | Project Lead Time (Years) | Earliest Projected In-Service Date (1) | For Resource Supply Option (2)
1 | Marion-Whiteville 230KV Line | Establish a new 230 kV line initially operated at 115 kV | Eng | PEC | 2007-06-01 | 11 | 5
2 | Lee Sub-Wommack 230 kV South Line | Reconductor existing line | Eng | PEC | 2008-05-01 | 13 | 5
3 | Durham 500 KV Sub | Establish 500 kV at Durham and loop-in the Mayo Plant-Wake 500 KV Line | Eng | PEC | 2008-06-01 | 31 | 5
4 | Clinton-Lee 230kV Line | Construct new line | Eng | PEC | 2009-06-01 | 21 | 5
5 | Rockingham-West End 230 kV Line | Construct Wadesboro Bowman School 230 kV Tap and uprate the portion between the tap and Rockingham 230 kV Sub | Eng | PEC | 2009-06-01 | 13 | 5
6 | Apex US1 - Amberly 115 kV Feeder | Extend current 115 kV feeder by constructing the Green Level - Amberly 115KV Section | Eng | PEC | 2010-06-01 | 20 | 5
7 | Cape Fear-Siler City 230 kV Line | Construct new 230 kV line | Eng | PEC | 2010-06-01 | 19 | 5
8 | Greenville-Kinston Dupont 230 KV Line | Construct new 230 kV line | Plan | PEC | 2011-06-01 | 18 | 5
9 | Henderson-Kerr Dam 115 kV Line | Construct new Warrenton 115 kV Tap & add line switches providing alternal service to Warrenton area | Plan | PEC | 2011-06-01 | 10 | 5
10 | Rockingham - West End 230kV East Line | Construct new 230 kV line | Plan | PEC | 2011-06-01 | 33 | 5
11 | Apex US1 - RTP 115 kV Line | Develop RTP 230/115kV Sub and construct Amberly-RTP 115 kV Section establising a new 115 kV line | Plan | PEC | 2012-06-01 | 11 | 5
[8 empty] | 2009 | Santee Cooper to CPLE
[8 empty] | 2012-06-01 | Duke to CPLE
|  | Reconductor Wateree - Great Falls 100 kV |  | Duke | 2011 |  |  | 2011 | (3)
|  | Replace Antioch 500/230 kV transformers #1 & #2 |  | Duke | 2014 | 15,000,000 to 20,000,000 | 5 | 2011 | 600 MW or 1200 MW from AEP to Duke
|  | Replace Parkwood 500/230 kV transformers #5 & #6 |  | Duke | 2015 | 15,000,000 to 20,000,000 | 5 | 2011 | Duke to CPLE
|  | Reconductor London Creek 230 kV lines (Peach Valley - Riverview #1 & #2) |  | Duke | 2016 | 20,000,000 to 25,000,000 | 3 | 2015 | Duke to CPLE
(1) Advancement of project based on 600 MW Resource Supply Options simulated in the 2006 reliability study
(2) 600 MW Resource Supply Option simulated in 2006 reliability study that results in the Earliest Projected In-Service Date
(3) Need for project not impacted by Resource Supply Options simulated in the 2006 reliability study
Note on D2: bguy: preliminary/ conceptual proposed planned committed under construction
Note on E2: bguy: Duke PEC
Note on G2: bguy: Estimate of fully loaded cost.
Note on H2: bguy: From study, engineering to in-service.