NC Transmission Planning Collaborative

Planning Work Group (PWG)

Meeting Minutes

June 14, 2007

Progress Energy Offices

Aberdeen, NC

10:00 AM – 3:00 PM Eastern

Attendees:

Bob Pierce							Duke Energy

Brian Moss							Duke Energy

Pam Kozlowski						Gestalt

Bryan Guy							Progress Energy

Rick Anderson						Fayetteville PWC

Lee Adams							Progress Energy

Laura Travison						Progress Energy

Mark Byrd							Progress Energy

Frank Gaffney						ElectriCities

Denise Roeder						ElectriCities

James Manning						NCEMC

Via Phone

Rich Wodyka							Gestalt

- ADMINISTRATIVE

- Mr. Guy called the meeting to order at approximately 10:20 AM.

- The group reviewed, modified and approved the May 9, 2007 PWG meeting minutes as drafted.  The group discussed the action items from that meeting.

- OSC MEETING

- Mr. Wodyka reported on the May 23rd OSC Meeting.

- Mr. Wodyka reported on the FERC Technical Conference for the Southeast region.

- GUIDELINES FOR INCLUDING LSE RESOURCES IN THE NCTPC BASE CASE PLANNING MODELS

- PWG reviewed and modified the guidelines and flow chart.  Changes will be brought to the July OSC meeting for approval.

ACTION ITEM:  Prior to the OSC meeting, Ms. Kozlowski to finalize wording and changes to ensure that the guidelines and flow chart are consistent.

- REPORT ON STATUS OF PROJECTS IDENTIFIED IN THE 2006 COLLABORATIVE PLAN

- The group reviewed the NCTPC update on the major projects in the Collaborative Transmission Plan.

ACTION ITEM:  Mr. Guy to bring update on the major projects in the Collaborative Transmission Plan to OSC for their review and to ask the OSC whether the update should be posted on the NCTPC public website.

- 2007 SOLUTION DEVELOPMENT

- PWG discussed transmission service requests in PEC’s queue that are either newly confirmed or nearing confirmation (400MW and 200MW, respectively) and whether they should be included in the 2007 study process.  PWG agreed this information should be taken into account in the 2007 study, and the best approach for doing this is to incorporate it as part of a new resource supply option scenario to be analyzed.

- PWG discussed including the Richmond CT request in the 2007 study process.

ACTION ITEM:  Duke and Progress to run 1200MW Duke to Progress resource supply option case with the transmission upgrades indicated in Appendix 3 of the 2006 Supplemental Report.  Duke and PEC to run a screen without the upgrades initially and later assess what Appendix 3 projects to include in a second study.  Mr. Guy to recommend to the OSC that this additional resource supply option case be developed and screened.  Ms. Kozlowski will update work plan to reflect impact on the 2007 schedule of studying the additional case.

ACTION ITEM:  PEC to verify that the operating procedures in Camden, Rockingham-West End and Marion areas solve the problems in those areas that were identified in the 2012 and 2016 base cases and 2016 resource supply option cases.

- PWG discussed potential solutions to the problems that Duke and PEC identified in the 2012 and 2016 base cases and 2016 resource supply option cases.

ACTION ITEM:  PEC to look at several scenarios to solve the Marion-Whiteville line issue.  PEC to look at tying Brunswick 1 and 2 together when one unit is off line.  PEC to look at dropping the Weatherspoon to Brunswick 230kV line into the Delco Sub.

ACTION ITEM:  Duke to check dropping 500kV to 230kV at Buck Steam Station or drop 500kV to 230kV at Winecoff to Marshall 230kV line as second option.

- 2008 STUDY ASSUMPTIONS

ACTION ITEM:  The consequences of a double-circuit common tower (DCT) contingency on the PEC system and on the Duke system are different due to the design of each of the systems and justify the different treatment of  DCT contingencies on the two systems.  Duke and PEC to draft explanation of this and to provide data on occurrences of DCT contingencies for the next PWG meeting.

ACTION ITEM:  PEC to get operations to speak at next meeting and bring loop flow data.

- PWG agreed that there was no need to investigate the in-rush component of TRM as PEC does not use the in-rush component.

ACTION ITEM:  PEC and Duke to exchange information on transformer rating methodologies.

- OTHER ITEMS

ACTION ITEM:  Mr. Guy to request that the OSC review the draft request to Yadkin for transmission planning information and request guidance from the OSC regarding next steps with Yadkin.

- PWG discussed work plan and actions to be taken to stay on schedule, including beginning to summarize the transmission problems identified as preparation for the final report due later this year.

ACTION ITEM:  Duke and PEC to summarize problems indicated on the results spreadsheet and analyze solutions proposed to resolve the issues in preparation for July PWG meeting.

- Ms. Kozlowski briefly discussed the FERC Order 890 document posting requirements.

Mr. Guy adjourned meeting at approximately 3:11 PM.