## Assigned & Active
Item | Date | Action | Assigned to | Due Date | Status
4 | 2007-09-12 | PEC to provide TRM parallel path historical data. | BG | 2007-09-28
12 | 10/17/07 & 12/6/07 | Contact PEC legal regarding responding to Kim Jones' questions on southern VA-NC constraint in DOE congestion report. | BG & MB
18 | 2007-10-17 | PEC operations has a few lines w/emergency ratings. Investigate using emergency ratings in planning. | BG
19 | 2007-10-17 | Present scope to PWG for PEC internal study on transformer ratings. | BG
20 | 2007-10-17 | Present options for modeling TRM in the new process that PEC operations is implementing for determing AFC/ATC. | PEC
35 | 2007-11-15 | Frame scope for cost estimate discussion w/OSC. | ALL | 2008-01-08

## Complete
Item | Date | Action | Assigned to | Due Date | Complete
46 | 2007-12-06 | Draft 2008 schedule & work plan for review at 1/8/08 PWG mtg. | PK | 2008-01-04 | Complete 1/7/08
45 | 2007-12-06 | Draft 2008 Study Scope for review at 1/8/08 PWG mtg. | JM | 2008-01-04 | Complete 12/12/07
44 | 2007-12-06 | Incorporate PWG comments in TAG ppt & distribute to OSC. | PK | 2007-12-11 | Complete 12/11/07
43 | 2007-12-06 | Provide comments on TAG ppt. | ALL | 2007-12-10 | Complete 12/10/07
42 | 2007-12-06 | Revise TAG ppt per PWG mtg. Distribute to PWG for comment. | PK | 2007-12-07 | 2007-12-07
41 | 2007-12-06 | Distribute draft 2007 Report & Appendices to PWG, OSC & TAG. | PK | 2007-12-07 | 2007-12-07
40 | 2007-12-06 | Finalize lower voltage facility recommendation via e-mail for 12/13/07 OSC mtg. | ALL | 2007-12-10 | Complete 12/10/07
39 | 2007-12-06 | Modify lower voltage facility recommendation to OSC. | RP | 2007-12-07 | 2007-12-07
38 | 2007-12-06 | Distribute Attachment K filing to PWG. | PK | 2007-12-07 | 2007-12-07
37 | 2007-12-06 | Develop one page scope of PEC West import study. | BM | 2007-12-13 | Complete 12/10/07
36 | 2007-11-15 | Develop recommendation/scope for studying implications/impact of Richmond CC & new 230 kV line. | ALL | 2007-12-06 | Complete 12/6/07, presented to OSC 12/13/07
34 | 2007-11-08 | Develop RSOs, model years & base interchange for Progress West import study. | PEC & Duke | 2007-11-26 | Complete 12/6/07
33 | 2007-11-08 | Distribute TAG ppt to OSC | BG | 2007-11-12 | 2007-11-12
32 | 2007-11-08 | Update TAG ppt & distribute to PWG for comment. | PK | 2007-11-09 | 2007-11-09
31 | 2007-11-08 | Distribute 2007 report & appendices ro rhw OSC. | BG | 2007-11-09 | 2007-11-09
30 | 2007-11-08 | Update 2007 report & appendices based on 11/8 PWG mtg & distribute to PWG. | PK | 2007-11-09 | 2007-11-09
29 | 2007-11-08 | Distribute 2008 Study Methodology recommendation to OSC. | BG | 2007-11-13 | 2007-11-13
28 | 2007-11-08 | Update 2008 Study Methodology recommendation w/section on lower voltage facilities & distribute to PWG for comment. | PK | 2007-11-09 | 2007-11-12
27 | 2007-11-08 | Distribute next version of Attachment K & cost allocation attachment to PWG when they become available. | PK |  | 2007-11-13
26 | 2007-11-08 | Distribute comments on October PWG miuntes to PWG for comment. | PK | 2007-11-09 | 2007-11-10
25 | 2007-10-29 | Comment on 10/29 draft of 2007 report & appendices. | ALL | 2007-11-02 | 2007-11-02
24 | 2007-10-29 | Update 2007 report & appendices, distribute to PWG. | PK | 2007-10-29 | 2007-10-29
23 | 2007-10-29 | Provide description of Wateree operating guide for 2007 report. | RP | 2007-10-29 | 2007-10-29
22 | 2007-10-29 | Send e-mail to OSC summarizing cost estimate alternatives & requesting guidance. | BG | 2007-10-31 | 2007-10-31
21 | 2007-10-29 | PEC comment on Duke scope for PEC West import study & distribute to PWG. | BG | 2007-10-31 | N/A, see item 37
17 | 2007-10-17 | Provide revised draft of 2007 report & appendices to PWG for reiview/comment. | PK | 2007-10-22 | 2007-10-22
16 | 2007-10-17 | Distribute e-mail correspondence with Kim Jones regarding the southern VA-NC constraint to the PWG. | PK | 2007-10-22 | 2007-10-22
15 | 2007-10-17 | Sub-group of PWG to decide on common cost basis for reporting the cost of a project. | BG, MB, BP |  | N/A, kicked up to OSC, See item 22
14 | 2007-10-17 | Provide telecon number for 10/29 PWG telecon. | LT |  | 2007-10-19
11 | 2007-10-17 | Provide comments to PK on 2008 Study Recommendations prior to 10/29 PWG telecon. | ALL |  | 2007-10-29
10 | 2007-10-17 | Send new draft of 2008 Study Recommendations for the OSC with updated TRM & transformer language. Send to PWG for comment. | PK | 2007-10-19 | 2007-10-26
9 | 2007-10-17 | Email L Travison August & September 2007 minutes approved at 10/17 PWG meeting. | BG |  | Complete
7 | 2007-09-12 | Update draft 2007 report & appendices B & C. | PEC & Duke | 2007-10-22 | Complete
6 | 2007-09-12 | Send draft 2007 report to PWG & identify holes that need to be filled by Duke & PEC. | PK | 2007-09-28 | Complete 1st draft 9/28/07, 2nd draft 10/4/07
5 | 2007-09-12 | PEC to provide solutions for the impacts found in their generation RSOs. | BG | 2007-10-17 | Complete
3 | 2007-09-12 | PEC to draft a paragraph on their transformer rating effort & recommend change for 2008. | BG | 2007-10-17 | Complete
2 | 2007-09-12 | Send the TAG ppt to the OSC. | BG | 2007-09-12 | Complete
1 | 2007-09-12 | Review & modify TAG ppt. | PK | 2007-09-12 | Complete