## Assigned & Active
Item | Date | Action | Assigned to | Due Date | Status
4 | 2007-09-12 | PEC to provide TRM parallel path historical data. | BG | 2007-09-28
12 | 10/17/07 & 12/6/07 | Contact PEC legal regarding responding to Kim Jones' questions on southern VA-NC constraint in DOE congestion report. | BG & MB
18 | 2007-10-17 | PEC operations has a few lines w/emergency ratings. Investigate using emergency ratings in planning. | BG
19 | 2007-10-17 | Present scope to PWG for PEC internal study on transformer ratings. | BG
20 | 2007-10-17 | Present options for modeling TRM in the new process that PEC operations is implementing for determing AFC/ATC. | PEC
35 | 2007-11-15 | Frame scope for cost estimate discussion w/OSC. | ALL | 2008-01-08
47 | 2008-01-08 | Rewrite December PWG meeting minutes. | Mark B
48 | 2008-01-08 | Compile & distribute screening results for the Progress West import study. | Joey W & Brian M | 2008-01-28 | Complete
49 | 2008-01-08 | Set up PWG conference call for Jan 30th | Bob B |  | Complete
50 | 2008-01-08 | Draft supplemental report sections that discuss Richmond Combined Cycle addition & Jacksonville Static VAR Compensator. | PEC
51 | 2008-01-08 | Request direction from OSC on the potential impact of the RPS wind generation requirement & what wind cases should be modeled for the 2008 study. | Bob B | 2008-01-16 | Complete
52 | 2008-01-08 | Review scope & work plan, provide comments to Pam K. | PWG | 2008-01-11 | Complete
53 | 2008-01-08 | Provide a write-up on methodology used in 2007 study for developing nominal costs, including a discussion of escalation assumptions, for the OSC. | Mark B | 2008-02-04
54 | 2008-01-31 | Distribute PEC Western Area Import Study. | Bob P | 2008-01-31 | Complete
55 | 2008-01-31 | Develop & distribute to PWG template for resource resource supply options. | Bob B | 2008-02-01 | Complete
56 | 2008-01-31 | Verify ratings of limiting elements in screening results for the Progress West import study. | Joey W | 2008-02-06

## Complete
Item | Date | Action | Assigned to | Due Date | Complete