## Assigned & Active
Item | Date | Action | Assigned to | Due Date | Status
53 | 1/8/08, 2/6/08, 3/5/08, 5/8/08 | Provide a write-up on methodology used in 2007 study for developing nominal costs, including a discussion of escalation assumptions, for the OSC. Update write-up per 3/5/08 & 5/8/08 mtgs. | Mark B | 2/4/08, moved to 5/14/08
57 | 2008-02-06 | Present results of PEC internal study on transformer ratings to the PWG. | PEC | July 08
86 | 2008-05-08 | Check with PEC staff re: status of internal study on transformer ratings. Report status of study to PWG at June mtg. | Mark B | 2008-06-13
58 | 2008-02-06 | Present PEC operations TRM implementation to the PWG. | PEC | June 08
87 | 2008-05-08 | Check with Phil Creech re: status of presenting PEC TRM implementation to the PWG. Report status to PWG at June mtg. | Mark B | 2008-06-13
65 | 2008-02-06 | Develop interchange for 13S and 18S base reliability cases. | Brian M & Lee | 3/12/08, moved to 5/8/08 | Complete
73 | 2008-03-05 | Include in Confidentiality Agreement that TAG Voting Member must meet the requirements of Section 9.4.3 of the planning attachments to Duke's & PEC's OATTs. | Pam & Rich | 2008-04-09
75 | 2008-03-05 | Work with siting engineers on identifying most feasible solutions to issues identified in Progress West Import Study & perform facilities studies. | Duke & PEC |  | Rec'd update from PEC at 5/8/08 mtg. Pursuing re-conductoring. Action item closed.
76 | 2008-04-09 | Determine which TPL events should be studied. Be prepared to discuss at May PWG mtg. | All | 2008-05-08 | Complete
77 | 2008-04-09 | Models developed for 13S & 18S base cases. | Duke & PEC | 2008-05-08 | Complete
78 | 2008-04-09 | Present at May PWG mtg results of recent large gen interconnection studies. | Duke & PEC | 5/8/08, PEC 6/17/08 | Complete for Duke on 5/8.
83 | 2008-05-08 | Distribute directions to June PWG mtg location in Greensboro. | Bob P | 2008-06-13 | Complete
84 | 2008-05-08 | Finalize 3/5/08 & 4/9/08 PWG mtg minutes & post. | Pam | 2008-05-13 | Complete
85 | 2008-05-08 | At May OSC mtg, request TOs ask their legal counsel whether state commission staff & FERC staff need to sign confidentiality agreement. | Rich | 2008-05-09 | Complete
88 | 2008-05-08 | Confirm Fayetteville load. | PEC | 2008-05-13 | Complete
89 | 2008-05-08 | 13S reliability case developed with 500 MW from Duke to Fayettville. | Duke | 2008-05-19 | Complete
90 | 2008-05-08 | Define injection points for wind resource supply option case. Report to PWG at June mtg. | Duke & PEC | 2008-06-17 | Complete
91 | 2008-05-08 | Provide results from reliability screenings (n-1) of: 13S w/500 MW from Duke to Fayetteville; 13S w/o Fayetteville transaction; 18S w/o Fayetteville transaction. Distribute to PWG prior to June mtg. | Duke & PEC | 2008-06-10 | Complete for PEC.
92 | 2008-05-08 | Provide results from TPL screenings of: 18S w/TRM; 18S w/o TRM. Distribute to PWG prior to August mtg. | Duke & PEC | 2008-07-30
93 | 2008-06-17 | Perform update of NCTPC major project listing | Duke & PEC | 2008-07-02

## Complete
Item | Date | Action | Assigned to | Due Date | Complete
18 | 2007-10-17 | PEC operations has a few lines w/emergency ratings. Investigate using emergency ratings in planning. | BG |  | Complete
19 | 2007-10-17 | Present scope to PWG for PEC internal study on transformer ratings. | BG |  | Complete
20 | 2007-10-17 | Present options for modeling TRM in the new process that PEC operations is implementing for determing AFC/ATC. | PEC |  | Complete 2/6/08
35 | 2007-11-15 | Frame scope for cost estimate discussion w/OSC. | ALL | 2008-01-08 | Replaced by item 53
47 | 1/8/08 & 2/6/08 | Rewrite December PWG meeting minutes. | Mark B | 2008-02-13 | Complete
48 | 2008-01-08 | Compile & distribute screening results for the Progress West import study. | Joey W & Brian M | 2008-01-28 | Complete
49 | 2008-01-08 | Set up PWG conference call for Jan 30th | Bob B |  | Complete
50 | 1/8/08 & 2/6/08 | Draft supplemental report sections that discuss Richmond Combined Cycle addition & Jacksonville Static VAR Compensator. | PEC | 2/27/08 & 3/17/08 | Complete 04/01/08
51 | 2008-01-08 | Request direction from OSC on the potential impact of the RPS wind generation requirement & what wind cases should be modeled for the 2008 study. | Bob B | 2008-01-16 | Complete
52 | 2008-01-08 | Review scope & work plan, provide comments to Pam K. | PWG | 2008-01-11 | Complete
54 | 2008-01-31 | Distribute PEC Western Area Import Study. | Bob P | 2008-01-31 | Complete
55 | 2008-01-31 | Develop & distribute to PWG template for resource resource supply options. | Bob B | 2008-02-01 | Complete
56 | 1/31/08 & 2/6/08 | Verify ratings of limiting elements in screening results for the Progress West import study. Address additional ratings issues from 2/6 PWG mtg. | Joey W | 2/6/08 & 2/13/08 | Complete
59 | 2008-02-06 | Provide IDEV to PEC of Duke's planned upgrades. | Brian M | 2008-02-07 | Complete
60 | 2008-02-06 | Rerun Progress West import screens w/ Duke's planned upgrades. | Joey W | 2008-02-18 | Complete
61 | 2008-02-06 | Check redispatch as a short term solution to Progress West import issues during construction of long term transmission solution. | Mark B | 2008-02-18 | Complete
62 | 2008-02-06 | Look at opening Canton-Pisgah line to mitigate common tower outage. | Joey W | 2008-03-05 | Complete 2/12/08
63 | 2008-02-06 | Screen alternative solutions identified at 2/6/08 PWG mtg for Progress West import study for 17/18W and 18S. | Brian M & Joey W | 2008-02-18 | Complete
64 | 2008-02-06 | Set up teleconference call for February 21 at 9 am. | Bob B | 2008-02-18 | Complete
66 | 2008-02-06 | Follow-up on independent co-op & muni input on resources for base cases (13S & 18S). | James & Denise | 2008-02-18 | Complete
67 | 2008-02-06 | Follow-up with Fayetteville on input on resources for base cases (13S & 18S). | Denise | 2008-02-18 | Complete
68 | 2008-02-06 | Update workplan based on 2/6 PWG mtg discussion, distribute to PWG for comment. | Pam | 2008-02-13 | Complete 2/6/08
69 | 2008-02-06 | Report on data Duke & PEC are willing to share in what form in response to TAG Member request. | Duke & PEC | 2008-02-20 | Complete 4/9/08
70 | 2008-02-06 | Follow up on question of why TRM values are posted from Operations but not from Planning, given that they are different values. | Mark B | 2008-03-05 | Complete 3/5/08
71 | 2008-02-06 | Follow up on question of whether PEC intends to continue to build for ANY common tower outage, including for the 2-mile long line identified as an issue in the West. | Mark B | 2008-03-05 | Complete 3/5/08
72 | 2008-02-06 | Revise input sheet for Enhanced Access Option requests. | Pam | 2008-03-05 | Complete 2/13/08
74 | 2008-03-05 | Describe alternative solutions for issues identified in Progress West Import Study for 2007 supplemental report. | Duke & PEC | 2008-03-14 | Complete
79 | 2008-04-09 | Turn around 2007 supplemental report & appendices for comment by PWG. Provide comments to Pam. Distribute updated report to OSC. | Pam PWG Pam | 4/10/08 4/10/08 4/11/08 | Complete
80 | 2008-04-09 | 1st draft of ppts for May TAG mtg. 2008 Study Activities 2007 Supplemental Report Regional Studies TAG Workplan | Denise Mark Duke&PEC Rich | 2008-04-23 | Complete
81 | 2008-04-09 | 1st draft of ppt on data sharing for May TAG mtg. Distribute to OSC. | Bob P & Pam | 2008-04-14 | Complete
82 | 2008-04-09 | Check w/legal depts on what/how much can be presented to the TAG regarding regional studies that Duke & PEC participate in. | Duke & PEC | 2008-04-23 | Complete