NC Transmission Planning Collaborative

Planning Work Group (PWG)

Meeting Minutes (DRAFT)

May 8, 2008

Electricities

Raleigh, NC

10:00 AM – 3:00 PM Eastern

Attendees:

Andy Fusco							ElectriCities

Laura Lee 							Duke Energy

Bob Pierce							Duke Energy

Bob Beadle							NCEMC

James Manning						NCEMC

Mark Byrd							Progress Energy

Joey West							Progress Energy

Lee Adams							Progress Energy

Rick Wodyka							Accenture

Pam Kozlowski						Accenture

Frank Gaffney						R.W. Beck

- ADMINISTRATIVE

- Bob Beadle called the meeting to order at 10:05 AM.

- The group reviewed and approved the March and April PWG meeting minutes as revised at the meeting.

ACTION ITEM:  Pam Kozlowski will finalize the meeting minutes and post them to the PWG site.

- OSC UPDATE

- Rich Wodyka gave an update of the items discussed on the OSC conference call on April 15th:

  - The TAG confidentially agreement will need to be signed by TAG members interested in seeing any confidential information presented as part of the TAG meeting materials.

  - The OSC commented that the table/discussion in the Supplemental Study showing changes from one year to the next is very helpful.

  - Any OSC/PWG members hosting a meeting should be reimbursed for expenses related to the meeting (lunch, etc.). Andy Fusco is the treasurer for the OSC and should be the contact for expense reimbursement.

  - The 500 MW western area (300 MW Progress Energy and 200 MW Duke) and 250 MW eastern area (Progress Energy) summer case assumptions for the wind sensitivity case were approved.

- PWG ACTION ITEMS

- Mark Byrd agreed to update the “Transmission Project Cost Estimates in the NCTPC” document reviewed at the March PWH meeting to include a discussion of escalation assumptions.

ACTION ITEM: Mark to email updated document to the PWG by 5/14.

- Mark Byrd agreed to check on the progress of the transformer ratings study and check with Phil Creech on an update to the TRM presentation.

ACTION ITEM: Mark to follow up with consultant on transformer ratings study and with Phil Creech, recommend meeting timeframe for an update presentation at the next PWG meeting.

- Mark Byrd also updated the PWG regarding developments with Progress Energy’s western area queue/study follow up, indicating that the prospect for locating new generation in the western control area did not look likely. Two transmission requests for 200 MW over 10 years and 100 MW over 5 years have been withdrawn and replaced with a single queue request for 300 MW over 25 years, resulting in serious re-evaluation of reconductoring the Shiloh-Pisgah-Asheville 230kV line as a long-term solution. Bob Pierce added that Duke’s scope of work for this option would include reinforcing 96 transmission towers and replacing an additional 40 towers.

ACTION ITEM: Mark and Bob to provide updates to the PWG as needed or as appropriate based on new developments, add to the collaborative plan if it becomes an approved project.  [NOTE: Do we mean “approved” (by whom)?  Or included in PEC’s plan?  Or something else?]

- TAG MEETING PREPARATION

- Pam reported that the draft 2007 Supplemental Study report has been released to the TAG for review. Rich will ask for comments at the TAG meeting within a week to ten days and will then distribute the final report to the TAG and post the final report to the NCTPC Reference Documents web page.

- Andy Fusco will replace Denise Roeder for the 2008 study activities presentation.

- 2008 STUDY

- Lee Adams reported that the interchange tables have been completed for the base cases. Bob Pierce pointed out that there are still a few discontinuities, including a 200 MW transfer for NCEMC and 600 MW for Fayetteville PWC from Duke. Bob Beadle responded that the 200 MW TSR for NCEMC was still good, the point-to-point transmission had not been requested/secured yet. Lee Adams/Joey West and Bob Pierce agreed to run the 2013 and 2018 base cases with the FPWC transfer included as a sensitivity.

ACTION ITEM: Duke and PEC to run cases (PEC to check FPWC load forecast numbers as well) and send out results to the PWG by 5/19.

- Joey West and Bob Pierce agreed to discuss point injection locations in the 2018 wind sensitivity case at the next meeting.

- Bob Pierce reported that the TPL standards drafting team still has a considerable amount of work to do before moving forward with a revised standard. Frank Gaffney recommended including the following TPL standards scope for the 2008 study:

  - P4 & P5: Loss of a 500kV line, followed by a system adjustment of generation, then loss of another 500kV line with no load shedding. Run case for combinations of Duke and PEC elements at 500kV.

  - Compare (N-2) event results to the applicable emergency ratings for 230kV and 500kV elements.

  - P3 & P8: Common tower/common breaker failure between two 230kV or 500kV elements.

ACTION ITEM: PWG members to consider TPL standard study scope and finalize specific items as suggested above at the next PWG meeting.

- LARGE GENERATOR INTERCONNECTION

- Bob Pierce mentioned a new modeling consideration—using a fictitious dumb generator in Florida or Manitoba so as to disperse the generation in the models so that it does not create a PWG internal area “bubble” effect.

- Bob gave an update on activity in Duke’s generation queue as follows:

  - Two generation requests in the 2010-2012 timeframe were made for Duke’s Buck Steam Plant (no significant upgrades), and Dan River (reconductoring needed for 100kV lines in the vicinity of the plant).

  - Duke’s request for Lee Nuclear Plant (2018 commercial operation date, 2200 MW) resulted in the need for fold in of the Pacolet-Catawba 230kV line, fold in of the 500kV line between Oconee and Newport, and bundling of the existing 230kV line from Lee into Catawba. An affected system study for this request was not needed.

  - Request for 800 MW at Cliffside (IGCC, 7/1/2012 in service date) will require a new tie into the Jocassee-McGuire 500kV line (the existing Cliffside generation is tied in at 100kV).

  - All requests listed above (except the Lee Plant) have been included in the base cases for the 2008 study.

  - Two other requests for generation at Ripp and Woodleaf are at the feasibility study stage. Adding generation at Woodleaf drives the need for the Dooley 500/230kV tie project and 230kV upgrades in the vicinity of the Winecoff Sub.

ACTION ITEM: Progress Energy will give an update on their generator queue at the June PWG meeting.

- 2008 WORK PLAN AND SCHEDULE

- PWG members reviewed the work plan and schedule, and concluded that the 2008 study process is on schedule.

- The next PWG meeting at Duke’s Fairfax Operations Center has been moved from June 4th to June 17th.

- OTHER ITEMS

Bob Beadle adjourned the meeting at approximately 2:55 PM.