| Period | PWG Activities | OSC Activities | TAG Activities |
| --- | --- | --- | --- |
| Jan 09 | 1/8 PWG Meeting 2009 STUDY SCOPE - Finalize 2009 Study Scope and provide final draft to OSC for their review and approval | 1/16 OSC Meeting 2008 STUDY REPORT - Distribute to the TAG and post on the NCTPC website the final 2008 Study Report 2009 STUDY SCOPE - Review and approve the 2009 Study Scope - Distribute approved 2009 Study Scope to TAG for their review and comment | 2008 STUDY REPORT - Receive final 2008 Study Report 2009 STUDY SCOPE - Receive final draft of the 2009 Study Scope for review and comment |
| Feb 09 | 2/4 PWG Meeting 2009 STUDY SCOPE - Update the 2009 Study Scope, if necessary 2009 CASE DEVELOPMENT - Begin developing base case models with new VSTE for 2014 and 2019 - All LSEs provide list of DNRs with dispatch order and a list of resource supply option scenarios to PWG | 2/12 OSC Meeting 2009 STUDY SCOPE - Review comments, if any, from TAG on 2009 Study Scope - Distribute to the TAG and post on the NCTPC website the final 2009 Study Scope - Request TAG provide input on proposed Enhanced Transmission Access scenarios and interfaces for study - Via e-mail correspondence, evaluate the TAG requests for enhanced transmission access scenarios and provide direction to the PWG on the 2009 Study Scope, if necessary - Finalize, approve and post 2009 Study Scope | 2009 STUDY SCOPE - Review and provide comments to the OSC on the 2009 Study Scope including the Study Assumptions; Study Criteria; Study Methodology and Case Development - Receive request from OSC to provide input on proposed Enhanced Transmission Access scenarios and interfaces for study - Provide input to the OSC on proposed Enhanced Transmission Access scenarios and interfaces for study by the end of February |
| Mar 09 | 3/4 PWG Meeting 2009 STUDY SCOPE - Receive input and direction from OSC related to TAG requests for enhanced transmission access scenarios - Update the 2009 Study Scope, if necessary 2009 CASE DEVELOPMENT - Complete developing base case models with new VSTE for 2014 and 2019 - Develop a recommendation to the OSC on resource supply option scenarios for inclusion in the 2009 studies 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Begin to develop the base case and LSEs’ resource supply option scenarios models TAG MEETING SUPPORT - Develop TAG meeting presentation materials | 3/12 OSC Meeting 2009 CASE DEVELOPMENT - Review and approve PWG recommendation on resource supply option scenarios for inclusion in the 2009 studies 2009 STUDY SCOPE - Provide feedback to TAG on what proposed Enhanced Transmission Access scenarios and interfaces will be included in the 2009 study TAG MEETING SUPPORT - Finalize the TAG meeting logistics and agenda items for the April TAG meeting |  |
| Apr 09 | 4/2 PWG Meeting 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Perform screens for the 2014 reliability base cases - Perform screens for the 2019 reliability base cases | 4/15 OSC Meeting 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Receive a progress report from the PWG | 4/15 TAG Meeting - Receive a progress report on the 2009 Planning study activities and results - Receive feedback from the OSC on what proposed Enhanced Transmission Access scenarios and interfaces will be included in the 2009 study |
| May 09 | 5/13 PWG Meeting 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Perform screens for the 2019 resource supply option scenarios | 5/19 OSC Meeting 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Receive a progress report from the PWG |  |
| Jun 09 | 6/2 PWG Meeting 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Complete the technical analysis and problem identification for the 2014 and 2019 reliability base cases 2009 SOLUTION DEVELOPMENT - Begin to determine and evaluate alternative solutions, estimated costs, and schedule estimates | 6/18 OSC Meeting 2009 TECHNICAL ANALYSIS, PROBLEM IDENTIFICATION and SOLUTION DEVELOPMENT - Receive a progress report from the PWG |  |
| Jul 09 | 7/9 PWG Meeting 2008 COLLABORATIVE PLAN UPDATE - PWG will prepare a report on the implementation status of the transmission projects identified in the 2008 Collaborative Plan for review with the OSC 2009 SOLUTION DEVELOPMENT - Finalize the information related to alternative solutions, estimated costs, and schedule for problems identified with the 2014 and 2019 reliability base cases and 2019 resource supply options 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Complete the technical analysis and problem identification for the 2019 resource supply options 2009 SELECTION OF SOLUTIONS - Begin to analyze and select preferred alternatives for 2009 Collaborative Plan | 7/xx OSC Meeting 2008 COLLABORATIVE PLAN UPDATE - OSC will review and comment on the PWG report on the implementation status of the transmission projects identified in the 2008 Collaborative Plan - OSC will provide the report to the TAG 2009 SOLUTION DEVELOPMENT - Receive a progress report from the PWG 2009 SELECTION OF SOLUTIONS - Receive a progress report from the PWG | 2008 COLLABORATIVE PLAN UPDATE - Receive update status of the upgrades in the 2008 Collaborative Plan |
| Aug 09 | 8/14 PWG Meeting 2009 SELECTION OF SOLUTIONS - Continue to analyze and select preferred solution alternatives for 2009 Collaborative Plan 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Begin to determine impacts of the 2019 resource supply option scenarios | 8/xx OSC Meeting 2009 SELECTION OF SOLUTIONS - Receive a progress report from the PWG |  |
| Sep 09 | 9/2 PWG Meeting 2009 TECHNICAL ANALYSIS and PROBLEM IDENTIFICATION - Complete sensitivity analysis of 2019 resource supply option scenarios 2009 REPORT DEVELOPMENT - Prepare report outline for the 2009 Collaborative Plan TAG MEETING SUPPORT - Develop TAG meeting presentation materials | 9/xx OSC Meeting 2009 SELECTION OF SOLUTIONS - Receive a progress report from the PWG 2009 REPORT DEVELOPMENT - Review and approve report outline of the 2009 Collaborative Plan TAG MEETING SUPPORT - Review and comment on the TAG meeting presentation materials | TAG Meeting 2009 TECHNICAL ANALYSIS, PROBLEM IDENTIFICATION and SOLUTION DEVELOPMENT - TAG will receive a progress report from the PWG on the 2009 study - TAG will be requested to provide input to the OSC and PWG on the technical analysis performed, the problems identified as well as proposing alternative solutions to the problems identified |
| Oct 09 | 10/6 PWG Meeting 2009 SELECTION OF SOLUTIONS - Finalize the selection of preferred solutions for inclusion in the 2009 Collaborative Plan 2009 REPORT DEVELOPMENT - Begin drafting the report on the 2009 Collaborative Plan | 10/xx OSC Meeting 2009 REPORT DEVELOPMENT - Receive a progress report from the PWG | 2009 TECHNICAL ANALYSIS, PROBLEM IDENTIFICATION and SOLUTION DEVELOPMENT - TAG will receive feedback from the OSC on any alternative solutions that were proposed by TAG members |
| Nov 09 | 11/4 PWG Meeting 2009 REPORT DEVELOPMENT - Finalize initial draft report on the 2009 Collaborative Plan and forward to OSC | 11/xx OSC Meeting 2009 REPORT DEVELOPMENT - Review the initial draft report on the 2009 Collaborative Plan and provide comments to the PWG |  |
| Dec 09 | 12/3 PWG Meeting 2009 REPORT DEVELOPMENT - Complete the 2009 Collaborative Plan Report based on OSC direction - Develop TAG meeting presentation materials | 12/xx OSC Meeting 2009 REPORT DEVELOPMENT - Review and finalize the 2009 Collaborative Plan Report - Distribute the final draft 2009 Collaborative Plan Report to the TAG for their review and comment TAG MEETING SUPPORT - Review and comment on the TAG meeting presentation materials | 2009 STUDY REPORT - Receive and comment on final draft of the 2009 Collaborative Transmission Plan report TAG Meeting - Receive presentation on the draft report of 2009 Collaborative Transmission Plan - Provide feedback to the OSC on the 2009 NCTPC Process - Review and comment on the 2009 TAG Activity Schedule |