NC Transmission Planning Collaborative

Planning Work Group (PWG)

Meeting Minutes

March 10, 2010

Conference Call

10:00 AM – 12:00 PM Eastern

Attendees:

Denise Roeder						ElectriCities

Bob Pierce							Duke Energy

Orvane Piper							Duke Energy

Bob Beadle							NCEMC

James Manning						NCEMC

Mark Byrd							Progress Energy

Lee Adams							Progress Energy

Kai Zai							Progress Energy

Rich Wodyka    						Accenture

Rick Anderson						FPWC

- ADMINISTRATIVE

- The February 4, 2010 PWG meeting minutes were approved without modification.

- Rich Wodyka updated the group on the 2/23/10 OSC meeting.

- The 2010 Work Plan was reviewed.  Modifications will be made based on the OSC’s acceptance of the PWG’s plan for studying the Southern Power Enhanced Access Request.

ACTION ITEM:   Rich Wodyka and Orvane Piper will update the Work Plan to account for the Southern Power Enhanced Access Request.

- The action item status was reviewed and updated – see attached.

- 2010 STUDY SCOPE

- PEC and Duke should complete their internal model development this week and have models available for merging.

- Interchange coordination has been completed by Duke and PEC.  All PWG members need to review the interchange for accuracy.

ACTION ITEM:   Orvane Piper will send the interchange tables to all PWG members.

ACTION ITEM:   PWG members will review the interchange table for accuracy.

- Off peak load level and the appropriate level to select for modeling to place the greatest stress on the transmission system from a thermal capacity point of view was discussed.  The upper range of off peak load conditions along with the stress of transporting the off peak offshore wind energy (maximum capacity) was judged to be the most severe condition.  Duke and Progress need to determine the specific common off peak load level to model.

ACTION ITEM:   Mark Byrd and Bob Pierce to exchange load duration curve data and determine the specific load level in each area for modeling in the off peak case.

- Discussed the PEC strawman for connecting the offshore wind resources to the transmission system.  The PWG decided to leave the strawman as is even though it did not allow for import of all 3000 MW under N-1 transmission system conditions.  The initial screening of the model will be done with the proposed strawman and the screening will identify any additional infrastructure that may be needed to meet N-1 criteria.

- The Enhanced Access Request from Southern Power and what year(s) to analyze was discussed.  Because the proposed service dates are so early in the 10 year planning horizon, the PWG feels it is better to use the earliest year model being used in the current study.  The 2015S case will be studied and the need for any upgrades to support future service extrapolated from the 2015 data.

| Request |  | SOURCE |  | SINK |  | MW |  | Service Dates |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Cleveland Co. site |  | CPLE |  | 1000 |  | 1/12 to 1/22 |
| 2 |  | Cleveland Co. site |  | DVP |  | 1000 |  | 1/12 to 1/22 |
| 3 |  | SOCO |  | DVP |  | 1000 |  | 1/12 to 1/22 |
| 4 |  | SOCO |  | CPLE |  | 1000 |  | 1/12 to 1/22 |

- OTHER ITEMS

- Bob Pierce contacted the Duke University student who expressed an interest in participating in the PWG’s work.  Participation Agreement and confidentiality agreement issues prevent the NCTPC from allowing his participation other than through the TAG.

- Discussed the failure of proposed NERC Reliability Standard TPL-001-1 to successfully pass ballot.

- Discussed the SAR for the “GOTO” revisions to multiple NERC Reliability Standards that is out for comment.

- Discussed the revision to NERC Reliability Standard FAC-003, Vegetation Management, which is out for comment.

- The next TAG meeting would be most appropriately scheduled for May based on the present status of PWG activities.

- Next PWG meeting is scheduled for 4/6/10, 10 AM at the Greensboro Fairfax Operating Center.

ACTION ITEM LOG

| Action Item | Responsibility | Status |
| --- | --- | --- |
| Supply contact information for Kai to the PWG. | Mark Byrd | Complete |
| Supply contact information for Orvane to the PWG. | Bob Pierce | Complete |
| Develop an exact list of unscrubbed generation to be retired. | Bob Pierce | Complete |
| Develop an exact list of unscrubbed generation to be retired. | Lee Adams | Complete |
| Provide 2015S peak load information for determining load ratio share allocation of wind energy to each area. | Bob Pierce | Complete |
| Provide 2015S peak load information for determining load ratio share allocation of wind energy to each area. | Lee Adams | Complete |
| Determine time of day for maximum capacity factor for off shore wind. | Orvane Piper | Complete |
| Determine off peak load level to be studied based on information from Orvane on time of day for maximum off shore wind capacity factor. | Bob Pierce | Complete |
| Determine off peak load level to be studied based on information from Orvane on time of day for maximum off shore wind capacity factor. | Lee Adams | Complete |
| Develop a strawman representing the infrastructure associated with bringing the energy onshore. | Mark Byrd | Complete |
| Review the revised 2010 Study Scope document and submit any additional revisions by 1/11/10. | All PWG members | Complete |
| Contact Duke University graduate student to discuss 2010 Study. | Bob Pierce | Complete |
| Coordinate interchange for models. | Lee Adams Orvane Piper | Complete |
| PEC will evaluate the strawman to develop changes so that N-1 criteria are met. | Mark Byrd | Complete |
| Comment on the PEC strawman proposal. | All PWG members | Complete |
| Update the Work Plan to account for the Southern Power Enhanced Access Request. | Rich Wodyka Orvane Piper |  |
| Send the interchange tables to all PWG members. | Orvane Piper |  |
| Review the interchange table for accuracy. | All PWG members |  |
| Exchange load duration curve data and determine the specific load level in each area for modeling in the off peak case. | Mark Byrd Bob Pierce |  |