NC Transmission Planning Collaborative

Planning Work Group (PWG)

Meeting Minutes

Fairfax Ops Center

April 12, 2010

10:00 AM – 3:00 PM Eastern

Attendees:

Denise Roeder						ElectriCities

Bob Pierce							Duke Energy

Orvane Piper							Duke Energy

Bob Beadle							NCEMC

James Manning						NCEMC

Mark Byrd							Progress Energy

Joey West							Progress Energy

Lee Adams							Progress Energy

Rich Wodyka    						Accenture

- ADMINISTRATIVE

- The March 10, 2010 PWG meeting minutes were approved without modification.

- Rich Wodyka updated the group on the 3/26/10 OSC meeting.

- The 2010 Work Plan was reviewed.

- The action item status was reviewed and updated – see attached.

- 2010 STUDY SCOPE

- PEC and Duke have completed their internal model development and models for 2015S, 2015W and 2020S will be developed.  Initial screening of the models can then begin.

ACTION ITEM:   Joey West to provide PEC models and contingency files to Orvane Piper for compiling joint models and contingency file.

ACTION ITEM:   Joey West and Orvane Piper to begin screening of joint models.

ACTION ITEM:   Joey West to develop PEC TRM cases and provide to Orvane Piper for screening.

ACTION ITEM:   James Manning to contact PJM for market dispatch information and idevs for update of MAPP and PATH projects which have been delayed.

- Interchange coordination has been completed by Duke and PEC and reviewed by NCEMC and NCMPA.  Some corrections are necessary.  NCEMC to assume 50 MW of short term firm transmission for Duke imports from Hamlet in all cases raising total import to 110 MW.  (Was previously identified as originating at Anson Plant.)

ACTION ITEM:   Orvane Piper will send revised interchange tables to all PWG members for review.

- Off peak load level will be modeled at 70% of 2015 summer peak based on evaluation of Duke and PEC’s load duration curves.  Approximately 80% of the year load is at this level or lower.

ACTION ITEM:   Joey West and Orvane Piper to create off peak case.

- The strawman for bringing wind energy on shore will initially be studied as is even though it is apparent that it will not allow for import of all 3000 MW under N-1 transmission system conditions.  The initial screening of the model will be done with the proposed strawman.  Stakeholder input will be used to determine whether it is necessary to identify the limit of wind energy that can be brought onshore while meeting N-1 criteria or to determine the cost of additional infrastructure that would be required.

ACTION ITEM:   Joey West to provide idevs for placing infrastructure identified in the strawman in the models.

- The Enhanced Access Request from Southern Power to analyze was discussed.  PEC will provide an economic dispatch for evaluation of the requests sinking in their area.  For those sinking in DVP and sourcing in SOCO, generation will be scaled to accommodate the transfer.

- SCRTP RESULTS

- The results of the latest SCRTP were reviewed.  The apparent causes of limits to south to north transfers from SCEG to CPLE or Duke are not obvious.  It appears to be related to dispatch of generation in SCEG’s southern most area.  The studies did not identify any new issues on the SCRTP/NCTPC interface.  There will be a need to evaluate the 100 kV tie lines between Duke and SCEG and the impact of VC Summer’s additional generation on the Wateree/Camden area.

- OTHER ITEMS

- Discussed impact of FERC March 18th Orders and NOPR’s.

- Discussed recent activity of the TPL-001-1 standard drafting team in response to related NERC orders on Footnote b, non-consequential load loss and the Pacificorp interpretation.

- Determined TAG 5/18/10 meeting topics and tentative assignments for presentations

  - Study scope & status - Denise

  - Enhanced Access Requests - Rich

  - Regional Study Status – SIRPP, PJM, SCRTP, EIPC, LTSG (multiple)

  - FERC Issues – (Rich to discuss with OSC)

- Next PWG meeting is scheduled for 5/5/10, 10 AM at the Greensboro Fairfax Operating Center.

ACTION ITEM LOG

| Action Item | Responsibility | Status |
| --- | --- | --- |
| Supply contact information for Kai to the PWG. | Mark Byrd | Complete |
| Supply contact information for Orvane to the PWG. | Bob Pierce | Complete |
| Develop an exact list of unscrubbed generation to be retired. | Bob Pierce | Complete |
| Develop an exact list of unscrubbed generation to be retired. | Lee Adams | Complete |
| Provide 2015S peak load information for determining load ratio share allocation of wind energy to each area. | Bob Pierce | Complete |
| Provide 2015S peak load information for determining load ratio share allocation of wind energy to each area. | Lee Adams | Complete |
| Determine time of day for maximum capacity factor for off shore wind. | Orvane Piper | Complete |
| Determine off peak load level to be studied based on information from Orvane on time of day for maximum off shore wind capacity factor. | Bob Pierce | Complete |
| Determine off peak load level to be studied based on information from Orvane on time of day for maximum off shore wind capacity factor. | Lee Adams | Complete |
| Develop a strawman representing the infrastructure associated with bringing the energy onshore. | Mark Byrd | Complete |
| Review the revised 2010 Study Scope document and submit any additional revisions by 1/11/10. | All PWG members | Complete |
| Contact Duke University graduate student to discuss 2010 Study. | Bob Pierce | Complete |
| Coordinate interchange for models. | Lee Adams Orvane Piper | Complete |
| PEC will evaluate the strawman to develop changes so that N-1 criteria are met. | Mark Byrd | Complete |
| Comment on the PEC strawman proposal. | All PWG members | Complete |
| Update the Work Plan to account for the Southern Power Enhanced Access Request. | Rich Wodyka Orvane Piper |  |
| Send the interchange tables to all PWG members. | Orvane Piper | Complete |
| Review the interchange table for accuracy. | All PWG members | Complete |
| Exchange load duration curve data and determine the specific load level in each area for modeling in the off peak case. | Mark Byrd Bob Pierce | Complete |
| Provide PEC models and contingency files to Orvane Piper for compiling joint models and contingency file. | Joey West |  |
| Begin screening of joint models. | Joey West Orvane Piper |  |
| Develop PEC TRM cases and provide to Orvane Piper for screening. | Joey West |  |
| contact PJM for market dispatch information and idevs for update of MAPP and PATH projects which have been delayed. | James Manning |  |
| Send revised interchange tables to all PWG members for review. | Orvane Piper |  |
| Create off peak case. | Orvane Piper |  |
| Provide idevs for placing infrastructure identified in the strawman in the models. | Joey West |  |