| Period | PWG Activities - Reliability Plan | PWG Activities - Enhanced Transmission Access Plan | OSC Activities | Tag Activities |
| --- | --- | --- | --- | --- |
| Sept05 - Nov05 | PWG recommends assumptions and criteria for the combined Duke/Progress reliability plan and submits to OSC for approval prior to 11/2 OSC meeting |  | 11/2: OSC meeting to discuss compare/contrast document submitted by PWG for reliability and enhanced access plans |  |
| Dec05 - Jan06 | PWG finalizes base case models with new VSTE LSEs provide preliminary list of scenarios to PWG PWG finalizes Reliability Study Scope document and summary of Reliability Plan Compare and Contrast document prior to 1/5 OSC meeting PWG makes recommendation to OSC on scenarios to study prior to 1/30 OSC meeting | PWG discusses assumptions and criteria for the combined Duke/Progress enhanced access plan and submits a summary of the compare/contrast document to 1/30 OSC meeting | 12/9: OSC continues discussion of enhanced access assumptions and criteria 1/5: OSC meeting to approve Reliability Study Scope document, resolve any issues in the summary of the Reliability Plan Compare and Contrast document, and discuss enhanced access assumptions and criteria 1/30: OSC meeting to finalize enhanced access assumptions and criteria | January meeting with TAG. Discuss: - Update on NCTPC Process - Comments on scope of TAG - Review 2006 activity schedule - Review reliability study scope - Request study scenarios for Enhanced Access Process |
| Feb06 – Mar06 | PWG begins work on base case and LSEs’ resource scenarios PWG performs screens for the reliability plan PWG reports status to OSC prior to 3/30 | PWG finalizes the Enhanced Transmission Access Study Scope document and submits to the OSC for approval 2/28 PWG receives preliminary list of enhanced access study requests on 2/28 | 2/10: Lists of requested enhanced access studies due from Participants and TAG (Carney & Locke to compile for 2/28) 2/28: OSC meeting to discuss/approve the Enhanced Transmission Access Study Scope document and the list of enhanced access projects/alternatives for preliminary study; OSC submits list to PWG to estimate study costs and schedules 3/30: OSC reviews PWG activities and progress | 2/10: TAG members submit lists of requested studies for Enhanced Access Process |
| Apr06-May06 | PWG determines alternatives, estimated costs, and schedule, and selects preferred alternatives for reliability plan | PWG develops estimated costs and schedules to perform preliminary enhanced access studies and provides to OSC prior to 5/1 PWG on 5/1 receives approved list of enhanced access requests to be studied in detail (can be delayed) | 5/1: OSC Meeting - Review cost/schedule of preliminary enhanced access studies submitted by PWG - Select enhanced access requests and alternatives to be studied in detail and submitted to PWG - Begin discussions of 2007/2008 budget for the Process and Gestalt 5/2: OSC informs TAG of study status | May TAG meeting: - Update on reliability studies - Feedback on approved list of enhanced access studies - Review enhanced access study scope |
| Jun06 | PWG reports reliability plan results to OSC prior to 6/30 & obtains OSC approval for preferred alternatives |  | 6/30: OSC Meeting - Approve 2006/2007 NCTPC budget; - PWG reports reliability plan results and obtains approval for preferred alternatives |  |
| Jul06-Aug06 | PWG provides final reliability plan & report to OSC prior to 7/30 | PWG begins enhanced access studies PWG finalizes potential alternatives to achieve desired levels of transfer capability based on selected enhanced access requests by 8/30 PWG on 8/31 - updates OSC on the potential alternatives identified and the respective planning-level estimates of construction costs and schedules for the enhanced access projects - receives OSC’s selection of enhanced access projects | 7/31: OSC approves final reliability plan 8/31: OSC receives PWG update on enhanced access studies, selects enhanced access projects, and provides selection back to PWG for refinement | August TAG Meeting - Review draft of Reliability Plan - Update on enhanced access studies |
| Sept06-Nov06 | PWG refines costs and schedules of reliability plan and reports results to OSC prior to 10/20 PWG integrates/iterates reliability plan with enhanced access plan and reports results to OSC prior to 11/20 | PWG refines costs and schedules of enhanced access projects/plan and reports results to OSC prior to 10/20 PWG integrates/iterates enhanced access plan with reliability plan and reports results to OSC prior to 11/20 | 9/7: OSC starts project cost allocation discussion 10/20: OSC reviews any refinements of enhanced access and reliability projects; OSC approves enhanced access projects/plan and submits to PWG for integration with reliability plan 11/20: OSC approves final reliability and enhanced access projects and combined reliability/enhanced access plan 11/21: OSC informs TAG of final collaborative plan |  |
| Dec06 |  |  | 12/15: OSC completes cost allocation and budget discussions for combined reliability and enhanced access plans | December TAG Meeting - Review final Collaborative Plan 12/31 Provide feedback to OSC on process |